## Mock data
Activity 8 mock data
Fictional training data. Review the fields before pasting selected rows into the activity prompt.
WBS ID | Parent WBS | Deliverable or work package | Acceptance criterion | Owner role | Estimated days
1.0 |  | Knowledge Hub Pilot | Sponsor accepts pilot outcomes | Project Manager | 80
1.1 | 1.0 | Governance package | Roles and approvals documented | Project Manager | 10
1.2 | 1.0 | Approved content set | Top 200 articles cleaned and approved | Knowledge Owner | 25
1.3 | 1.0 | Configured search experience | Priority requirements pass testing | IT Lead | 30
1.4 | 1.0 | Pilot training | 30 agents complete practice tasks | Service Lead | 8
1.5 | 1.0 | Pilot evaluation report | Sponsor accepts recommendation | Project Manager | 7