## Mock data
Activity 9 mock data
Fictional training data. Review the fields before pasting selected rows into the activity prompt.
Task ID | Task | Duration days | Predecessor | Resource | Constraint
T-01 | Approve charter | 2 |  | Sponsor | Must finish
T-02 | Confirm requirements | 5 | T-01 | Product Owner | As soon as possible
T-03 | Clean knowledge content | 12 | T-01 | Knowledge Team | As soon as possible
T-04 | Configure search | 10 | T-02 | IT Team | As soon as possible
T-05 | Load approved content | 4 | T-03,T-04 | IT Team | As soon as possible
T-06 | Security testing | 5 | T-05 | Security Team | As soon as possible
T-07 | Agent pilot | 10 | T-06 | Service Team | Start no earlier than day 35
T-08 | Evaluate pilot | 4 | T-07 | Project Manager | Must finish