## Mock data
Activity 10 mock data
Fictional training data. Review the fields before pasting selected rows into the activity prompt.
WBS ID | Cost item | Quantity | Unit | Rate SGD | Estimate basis | Confidence
1.1 | Project management | 40 | day | 900 | Internal rate card | High
1.2 | Content specialist | 55 | day | 650 | Internal rate card | Medium
1.3 | Platform configuration | 30 | day | 1100 | Vendor quotation | Medium
1.3 | Software licence | 12 | month | 2200 | Supplier price list | High
1.4 | Training delivery | 6 | session | 1800 | Training proposal | High
1.5 | Evaluation analyst | 8 | day | 750 | Internal rate card | Medium