## Mock data
Activity 11 mock data
Fictional training data. Review the fields before pasting selected rows into the activity prompt.
Metric | Baseline | Plan to date | Actual to date | Unit | Data date | Comment
Approved articles | 0 | 160 | 138 | count | 2026-12-04 | Review queue slower than planned
Configured requirements | 0 | 5 | 4 | count | 2026-12-04 | Audit-log feature pending
Budget spent | 0 | 92000 | 101500 | SGD | 2026-12-04 | Additional security work
Schedule elapsed | 0 | 60 | 67 | percent | 2026-12-04 | Security retest added
Critical defects | 0 | 0 | 2 | count | 2026-12-04 | Both assigned
Pilot users trained | 0 | 30 | 24 | count | 2026-12-04 | Second session rescheduled