## Mock data
Activity 18 mock data
Fictional training data. Review the fields before pasting selected rows into the activity prompt.
Risk ID | Cause | Uncertain event | Effect | Category | Early warning | Evidence
R-01 | Article ownership is unclear | Outdated content is loaded | Agents give incorrect answers | Quality | Overdue review dates exceed 10% | Content audit
R-02 | Vendor API limits are untested | Search traffic exceeds quota | Response time increases | Technical | Usage above 70% quota | Vendor documentation
R-03 | Pilot overlaps peak season | Agents cannot attend training | Adoption is delayed | Resource | Attendance below 80% | Operations calendar
R-04 | Security review capacity is limited | Approval is delayed | Go-live slips | Schedule | Review slot not booked | Resource plan
R-05 | Benefits baseline is incomplete | Savings cannot be proven | Sponsor withdraws support | Benefits | Baseline gaps remain | Measurement plan
R-06 | Single knowledge lead owns taxonomy | Lead becomes unavailable | Content work stops | People | No deputy assigned | RACI