## Mock data
Activity 20 mock data
Fictional training data. Review the fields before pasting selected rows into the activity prompt.
Variable | Unit | Low | Base | High | Probability high | Cost or schedule effect
Content cleanup effort | person-days | 35 | 50 | 75 | 0.3 | Cost
Vendor configuration | SGD | 28000 | 36000 | 52000 | 0.25 | Cost
Security remediation | SGD | 5000 | 18000 | 45000 | 0.2 | Cost
Training attendance | percent | 65 | 82 | 95 | 0.35 | Schedule
Search defect rate | percent | 2 | 6 | 14 | 0.25 | Schedule
API response time | seconds | 1.2 | 2 | 4.5 | 0.2 | Schedule
Article approval cycle | days | 2 | 5 | 11 | 0.3 | Schedule
Pilot duration | weeks | 3 | 4 | 7 | 0.25 | Cost
Adoption after pilot | percent | 45 | 70 | 88 | 0.4 | Benefits
Annual licence increase | percent | 0 | 5 | 12 | 0.2 | Cost