## Mock data
Activity 21 mock data
Fictional training data. Review the fields before pasting selected rows into the activity prompt.
Risk ID | Threat or opportunity | Priority | Current owner | Trigger | Response budget SGD | Constraint
R-01 | Threat | High | Knowledge Lead | Overdue reviews exceed 10% | 12000 | Go-live quality gate
R-02 | Threat | Medium | IT Lead | Quota use exceeds 70% | 8000 | Vendor contract
R-03 | Threat | High | Service Lead | Training attendance below 80% | 6000 | Peak roster
R-04 | Threat | High | Project Manager | Security slot not booked by 15 Oct | 15000 | Fixed launch date
R-05 | Threat | Medium | Benefits Owner | Baseline missing by pilot start | 4000 | Sponsor reporting
R-07 | Opportunity | Medium | Product Owner | Accuracy exceeds 90% | 10000 | Capacity for expansion