## Mock data
Activity 25 mock data
Fictional training data. Review the fields before pasting selected rows into the activity prompt.
Change ID | Request | Requester | Scope impact | Schedule days | Cost SGD | Quality impact | Risk impact | Decision status
CR-01 | Add a third product line | Sponsor | High | 15 | 28000 | More coverage but less pilot depth | Higher content risk | Pending
CR-02 | Add response export to PDF | Service Lead | Medium | 6 | 9000 | Improves audit evidence | Low technical risk | Pending
CR-03 | Move pilot two weeks earlier | Operations | Low | -14 | 14000 | Less test time | Higher launch risk | Pending
CR-04 | Remove zero-result dashboard | Vendor | Medium | -3 | -7000 | Reduces learning feedback | Higher benefits risk | Pending
CR-05 | Add bilingual content | Sponsor | High | 20 | 36000 | Wider access | Translation quality risk | Pending