## Slide 1
MASTER TRAINER SLIDES · NON-WSQ
Generative AI for Project Management
Course Code: C013
Conducted by Tertiary Infotech Academy Pte Ltd · UEN: 201200696W
Version v1.0 · 19 September 2026
© 2026 Tertiary Infotech Academy Pte Ltd. All rights reserved. · www.tertiarycourses.com.sg

## Slide 2
COURSE ADMINISTRATION
Welcome & Housekeeping
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
2

## Slide 3
YOUR TRAINER · GENERAL
About the Trainer
?
Your Trainer
General Trainer template — to be completed by the trainer
NAME
____________________________________________
TITLE / DESIGNATION
____________________________________________
QUALIFICATIONS
____________________________________________
AREAS OF EXPERTISE
____________________________________________
TRAINING & INDUSTRY EXPERIENCE
____________________________________________
CONTACT
____________________________________________
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
3

## Slide 4
YOUR TRAINER
About the Trainer
AA
Dr Alfred Ang
Principal Trainer Tertiary Infotech Academy Pte Ltd
ROLE
Principal Trainer, Tertiary Infotech Academy Pte Ltd
EXPERTISE
Project management, generative AI adoption and digital transformation.
DELIVERS
Courses on project management, business analysis and applied generative AI.
FOUNDER
Founder and lead instructor at Tertiary Infotech / Tertiary Courses.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
4

## Slide 5
ICE-BREAKER
Let's Know Each Other
1
Who you are
Your name, organisation and role.
2
What you run
The kind of projects you manage — size, industry and team.
3
What you use
Which GenAI tools you already use, and what for.
4
What you want
One project task you would most like GenAI to take off your hands.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
5

## Slide 6
HOUSEKEEPING
Ground Rules
1
Set your mobile phone to silent mode.
2
Participate actively — no question is too small.
3
Mutual respect: agree to disagree.
4
One conversation at a time.
5
Be punctual; return from breaks on time.
6
Full attendance — attend both days to get the most from the course.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
6

## Slide 7
COURSE PORTAL · LMS / TMS
Download Your Course Material
🔒 lms-tms.tertiaryinfotech.com
My Courses › Generative AI for Project Management
📊
Trainer Slides (PPT)
Download
📕
Learner Guide (PDF)
Download
🗓
Lesson Plan (PDF)
Download
🧪
Activities & Templates
Download
1
Go to lms-tms.tertiaryinfotech.com
2
Log in with the account emailed to you
3
Open this course from My Courses
4
Download the slides, Learner Guide and templates
5
Keep them open — refer to them during the activities
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
7

## Slide 8
TEMPLATE PACK
Download the Project Management Templates
1
What's in the pack
Charter, RTM, WBS and WBS Dictionary, Gantt, schedule network diagram, RACI, SEAM, tornado chart, decision tree, check sheet and control chart.
2
Where to get it
The shared course template pack link is on the LMS and in your Learner Guide.
3
When to download
Before the first activity — you will use these templates throughout both days.
4
Formats
Excel, Word and PowerPoint — open them in Office or Google Workspace.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
8

## Slide 9
THREE TOPICS · 25 GenAI ACTIVITIES
Course Outline
Topic 1 — Initiation & Planning
• Project & GenAI fundamentals
• 10 prompting patterns
• Charter & business case
• Stakeholders & RACI
• Requirements & RTM
• WBS & WBS dictionary
• Schedule & critical path
• Cost & budget
Topic 2 — Execution & Delivery
• Direct & manage work
• Manage project knowledge
• Quality & root cause analysis
• PDCA & DMAIC
• Optimise resources & budget
• Develop & manage the team
• Manage communications
Topic 3 — Risk & Closure
• Identify & analyse risk
• Tornado & decision trees
• Plan risk responses
• Procurement & contracts
• Monitor & control change
• Earned value analysis
• Control quality
• Close the project
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
9

## Slide 10
SCHEDULE · 9:30am – 5:30pm
Lesson Plan — 2 Days, 7.5 Instructional Hours per Day
Day 1
Day 2
• Day 1 — Initiation & Planning with GenAI
– Introduction, ground rules and course outline
– Topic 1: Project Initiation and Planning with GenAI
– Activities 1–10
– Lunch 1:00–1:30pm
– End of Day 1
• Day 2 — Execution, Risk & Closure with GenAI
– Day 1 recap
– Topic 2: Project Execution and Delivery with GenAI (Activities 11–17)
– Topic 3: Managing Project Risks with GenAI (Activities 18–25)
– Course recap and feedback
– End of Day 2
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
10

## Slide 11
FOUNDATIONS
Projects, Project Management & GenAI
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
11

## Slide 12
DEFINITION
What is a Project?
1
Creates something unique
A unique product, service or result — not business as usual.
2
Is time-limited
It has a definite beginning and a definite end.
3
Drives change
It moves the organisation from a current state to a future state.
4
Enables value creation
It delivers a business benefit that justifies the investment.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
12

## Slide 13
IN PRACTICE
Examples of Projects
1
Developing a software application
2
Building a new office
3
Filming a motion picture
4
Creating an advertising campaign
5
Creating new processes within a business unit
6
Rolling out a GenAI assistant to a service team
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
13

## Slide 14
SCALE
Small Projects
What makes a project 'small'
Examples
• Typically less than six months
• Relatively limited resources
• Limited interdependency with other projects
• Limited strategic impact
• Relatively informal — reduced documentation and process
• The PM may have to lead AND work directly on the project
• May be scaled into a larger but separate project
• Develop a prototype to showcase an innovative idea
• Implement a jig for product qualification
• Construct a new pavement in the garden
• Set up a booth for an exhibition
• Pilot a GenAI tool with one team before rollout
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
14

## Slide 15
REFLECTION
What small projects have you been involved in?
Turn to the person next to you. Share one project — what made it a project rather than routine work, and what made it hard.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
15

## Slide 16
DEFINITION
What is Project Management?
1
The practice
Initiating, planning, executing, controlling and closing the work of a team to achieve specific goals and meet specific success criteria at a specified time.
2
Why it exists
Projects power change and enable the organisation to achieve its business objectives.
3
Who is accountable
The project manager. GenAI changes HOW the work is done — never WHO is accountable for it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
16

## Slide 17
CHANGE ONE, YOU CHANGE THEM ALL
The Triple Constraint
1
Scope
What the project will deliver.
2
Time
When it must be delivered.
3
Cost
What the organisation will spend.
4
Quality
Sits at the centre — change any one constraint and quality is what usually absorbs it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
17

## Slide 18
THE PMI TALENT TRIANGLE
Project Manager Competencies
Ways of Working
• Agile, Waterfall and hybrid
• Tailoring the method to the environment
• Knowing which approach fits
Power Skills
• Collaborative leadership
• Effective communication
• Influence without authority
Business Acumen
• Priority and cost vs benefit
• Making good business decisions
• Continuous learning
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
18

## Slide 19
PMBOK 7
The 12 Project Management Principles
1
Be a diligent, respectful and caring steward
2
Create a collaborative project team environment
3
Effectively engage with stakeholders
4
Focus on value
5
Recognise, evaluate and respond to system interactions
6
Demonstrate leadership behaviours
7
Tailor based on context
8
Build quality into processes and deliverables
9
Navigate complexity
10
Optimise risk responses
11
Embrace adaptability and resilience
12
Enable change to achieve the envisioned future state
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
19

## Slide 20
WHAT ACTUALLY DRIVES OUTCOMES
Project Success Depends On
1
Organisational project maturity
2
Project manager effectiveness
3
Funding and resource availability
4
Team member skill levels
5
Collaboration and communication with stakeholders
6
Understanding of the core problem and related needs
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
20

## Slide 21
TWO DIFFERENT THINGS
Project Life Cycles
How the project is structured
How you deliver
• Project Life Cycle
– The phases the project passes through
– May have phase gates — review performance against objectives
– At each gate: proceed, change or stop
• Development Life Cycle
– Predictive (Waterfall)
– Iterative
– Incremental
– Agile
– Hybrid
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
21

## Slide 22
CHOOSING YOUR APPROACH
Waterfall vs Agile
Predictive
Adaptive
• Predictive / Waterfall
– Requirements fixed up front
– Performs each process once for the whole product
– Change is controlled through change requests
– Suits well-understood, stable work
• Adaptive / Agile
– Requirements emerge and are re-prioritised
– Performs each process once per increment
– Change is expected and welcomed
– Suits high-uncertainty work
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
22

## Slide 23
WHAT AGILE ACTUALLY MEANS
Agile = Incremental + Iterative
1
Incremental
Small, regular releases of working value rather than one big-bang delivery.
2
Iterative
Reflecting and improving regularly — each cycle makes the product better.
3
High uncertainty
Agile suits work where the requirements cannot be fully known up front.
4
Many origins
Agile draws on Scrum, XP, Kanban, Lean and DSDM.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
23

## Slide 24
WHO DOES THE WORK
The Project Team
Makeup
Skills
• Team makeup varies
– By organisational culture, location and scope
– Full-time or part-time members
– Includes generalists and specialists
– Co-location helps — learning by osmosis
• Skill requirements
– Ensure relevant skill sets are present
– Avoid single points of failure
– Create cross-functional teams
– Use generalising specialists — 'T-shaped' people
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
24

## Slide 25
GENERATIVE AI
GenAI for the Project Manager
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
25

## Slide 26
THE ESSENTIALS
What is Generative AI?
1
Creates new content
GenAI tools generate text, images, code, tables and ideas from a prompt.
2
Trained on patterns
They predict likely output from patterns in training data — they do not 'know' your project.
3
Conversational
You refine the output by refining the prompt — it is a dialogue, not a search box.
4
Confidently wrong
They will produce fluent, plausible output that is factually wrong. Verification is your job.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
26

## Slide 27
YOUR TOOLKIT
The GenAI Tools You'll Use
1
ChatGPT
chat.openai.com — general drafting, tables, analysis.
2
Claude
claude.ai — long documents, structured reasoning, critique.
3
Gemini
gemini.google.com — research-backed drafting and Workspace integration.
4
Microsoft Copilot
copilot.microsoft.com — drafting inside Office documents.
5
Project Manager Buddy GPT
A purpose-built PM GPT used throughout this course.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
27

## Slide 28
YOUR COURSE GPT
Project Manager Buddy GPT
1
What it is
A purpose-built GPT for project management, used throughout this course's activities.
2
Why use it
It already knows PM terminology, artifacts and process — so your prompts can be shorter.
3
Where to find it
Open it from the link in your Learner Guide, or search 'Project Manager Buddy' in the GPT store.
4
Still verify
It is still a GenAI tool: it will invent figures and sources. Check everything.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
28

## Slide 29
WHY GenAI FOR PROJECT MANAGEMENT
“
The goal of GenAI is to take a project professional's mundane tasks and make them easy, like 'here you go, this is done.' Learning to leverage it ultimately increases the value of the project professional to the organization, because not only is it saving the professional's precious time, but it is also empowering the professional to focus on strategic aspects of the job that no one else can do.
John Signo, VP DMT Delivery Lead, Bank of America, USA
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
29

## Slide 30
WHY GenAI FOR PROJECT MANAGEMENT
“
I don't think GenAI can run a project, but as a reviewer of project work, it can find errors much faster than humans — reviewing schedules, plans and project boards to identify risks, scheduling challenges, unknown dependencies and mistakes.
John Signo, VP DMT Delivery Lead, Bank of America, USA
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
30

## Slide 31
WHY GenAI FOR PROJECT MANAGEMENT
“
I use GenAI to augment complex decision-making — to see things from multiple angles, find innovative approaches and get intelligent suggestions I would not have reached alone.
Yuliya Zhevno, Project and Change Management Consultant, Re:Work Consulting, Kazakhstan
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
31

## Slide 32
SIX HIGH-VALUE USES
Where GenAI Helps a Project Manager Most
1
Drafting
Charters, plans, reports, communications — a good first draft in seconds.
2
Structuring
Turning messy input into a WBS, RTM, risk register or RACI matrix.
3
Ideation
Generating risks, requirements, options and root causes you would not think of.
4
Reviewing
Auditing your own plans for gaps, ambiguity and missing dependencies.
5
Analysing
Comparing alternatives and explaining the trade-offs in a table.
6
Communicating
Rewriting the same message for very different audiences.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
32

## Slide 33
KNOW THE LIMITS
What GenAI Does Well — and Badly
Use it for this
Never trust this
• Does well
– Producing a structured first draft fast
– Generating breadth — many options and ideas
– Reformatting and summarising
– Explaining a concept or technique
– Reviewing your work for gaps
• Does badly
– Anything requiring facts about YOUR organisation
– Arithmetic — verify every calculation
– Citing real sources — it invents them
– Judging what matters in your context
– Anything about a specific named person
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
33

## Slide 34
THE GOLDEN RULE
You remain accountable for every output.
GenAI drafts; you decide. Every figure, source and recommendation that leaves your hands is yours — not the model's.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
34

## Slide 35
GOVERNANCE
Using GenAI Responsibly at Work
1
Confidentiality
Never paste client data, personal data or commercially sensitive information into a public tool.
2
Check your policy
Your organisation may mandate an enterprise tool with data protections.
3
Verify facts
Treat every figure, date and citation as unverified until you check it.
4
Disclose appropriately
Be transparent where AI materially shaped a deliverable.
5
Bias
Output reflects patterns in training data — review recommendations about people especially carefully.
6
Keep the human in the loop
Approval decisions stay with people, not models.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
35

## Slide 36
PROMPTING
Ten Prompting Patterns for Project Managers
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
36

## Slide 37
FIVE PARTS
Anatomy of a Good Prompt
1
ROLE — who the AI should act as
▶
2
CONTEXT — your project, industry and constraints
▶
3
TASK — exactly what to produce
▶
4
FORMAT — table, list, document, length
▶
5
CHECK — mark assumptions, cite sources
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
37

## Slide 38
OVERVIEW
The Ten Patterns
1
Persona
Frame the output from the perspective of a specific project role — or a non-human entity such as project management software.
2
Question Refinement
Ask GenAI to improve your question when there is no clarity about the problem you are trying to solve.
3
Flipped Interaction
Let GenAI interview you — it asks the questions, one at a time, to find the gaps in your thinking.
4
Alternative Approaches
Generate several options, then compare their pros and cons before you decide.
5
Cognitive Verifier
Force GenAI to break a complex question into smaller sub-questions and then combine the answers.
6
Fact Check List
For outputs that rest on external information, require the facts to be listed separately with links to sources.
7
Visualisation Generator
Have GenAI write the prompt for a text-to-image or diagram tool so you can visualise project information.
8
Reflection
Ask for the reasoning and assumptions behind a recommendation — essential for risk and people decisions.
9
Risk Matrix Template
A long-form template that produces a complete, industry-specific risk matrix in one pass.
10
Decision Making Template
Decompose a complex decision into smaller questions that together answer it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
38

## Slide 39
PROMPTING PATTERN
Pattern — Persona
Frame the output from the perspective of a specific project role — or a non-human entity such as project management software.
EXAMPLE PROMPT
Act as a stakeholder of the project. Perform an assessment of the project charter and provide a list of recommendations to improve scope clarity and completeness.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
39

## Slide 40
PROMPTING PATTERN
Pattern — Question Refinement
Ask GenAI to improve your question when there is no clarity about the problem you are trying to solve.
EXAMPLE PROMPT
Within the scope of creating a cost-benefit analysis of outsourcing (total cost: US$60,000) versus in-house hiring (total cost: US$70,000), suggest a better version of the question to be used.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
40

## Slide 41
PROMPTING PATTERN
Pattern — Flipped Interaction
Let GenAI interview you — it asks the questions, one at a time, to find the gaps in your thinking.
EXAMPLE PROMPT
I would like you to ask questions to help with my preparation for a project update with my stakeholders. Ask me questions one at a time so you can build the next question based on my responses.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
41

## Slide 42
PROMPTING PATTERN
Pattern — Alternative Approaches
Generate several options, then compare their pros and cons before you decide.
EXAMPLE PROMPT
I am a construction project manager experiencing a delay in completion of some tasks. I want to identify the root cause(s) of the problem. Suggest at least two options to deal with the problem(s) identified and compare the pros and cons of each. Present the results in a table.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
42

## Slide 43
PROMPTING PATTERN
Pattern — Cognitive Verifier
Force GenAI to break a complex question into smaller sub-questions and then combine the answers.
EXAMPLE PROMPT
A software development project has a US$100,000 budget and a timeline of six months. After three months the actual cost is US$60,000 and the project is 50% complete. What are the risks of not completing on time and on budget? Am I over or under budget? Am I behind or ahead of schedule? What is the earned value and estimate to complete? Combine the answers to produce the final answer to the first question.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
43

## Slide 44
PROMPTING PATTERN
Pattern — Fact Check List
For outputs that rest on external information, require the facts to be listed separately with links to sources.
EXAMPLE PROMPT
Generate a list of the 10 most common frequent-flier challenges in the airline industry based on facts. The set of facts should be inserted at a specific point in the output and correctly show links to sources.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
44

## Slide 45
PROMPTING PATTERN
Pattern — Visualisation Generator
Have GenAI write the prompt for a text-to-image or diagram tool so you can visualise project information.
EXAMPLE PROMPT
I want to generate a prompt that I can provide to a diagram tool to visualise the 10 most common sources of project scope creep for my project kickoff presentation.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
45

## Slide 46
PROMPTING PATTERN
Pattern — Reflection
Ask for the reasoning and assumptions behind a recommendation — essential for risk and people decisions.
EXAMPLE PROMPT
I need to provide feedback to a project team member who made a mistake with financial implications. Explain the reasoning and assumptions behind your recommendation on how to approach this meeting with them.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
46

## Slide 47
PROMPTING PATTERN
Pattern — Risk Matrix Template
A long-form template that produces a complete, industry-specific risk matrix in one pass.
EXAMPLE PROMPT
Imagine you are an expert project manager in the [Industry], focusing on [Project type] projects. Develop a comprehensive risk matrix. For each risk include: Risk name, Description, Level of impact (high/medium/low) and Likelihood (high/medium/low). Cover budget, schedule, technology, regulatory, resource, scope creep, stakeholder, data security, quality and external dependency categories. Output as a table.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
47

## Slide 48
PROMPTING PATTERN
Pattern — Decision Making Template
Decompose a complex decision into smaller questions that together answer it.
EXAMPLE PROMPT
Imagine you are an expert project manager in the [Industry] working on a [Project type] project. Break the complex question "[Complex question?]" into smaller questions that collectively answer it. Consider the range of outcomes, sources of resistance, risks and mitigation plans, and key milestones. Provide one-to-three-sentence answers to each, then ask me where I would like to go deeper.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
48

## Slide 49
TOPIC 01 · ACTIVITY 1
Prompting Patterns for Project Managers
ACTIVITY 1
Work through the ten prompting patterns on a project of your own. You will see the same question answered badly by a vague prompt and well by a structured one, and you will keep a personal prompt library for the rest of the course.
You'll produce
A personal prompt library of 10 tested prompts, each with the output it produced and your critique.
Tools: ChatGPT · Claude · Gemini · Copilot · Project Manager Buddy GPT
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
49

## Slide 50
TOPIC 01 · ACTIVITY 1
Prompting Patterns for Project Managers
ACTIVITY 1
PROMPT GenAI WITH
Act as a stakeholder of the project. Perform an assessment of the project charter and provide a list of recommendations to improve scope clarity and completeness.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
50

## Slide 51
ACTIVITY 1 · CHECK YOUR WORK
Prompting Patterns for Project Managers
✅ Check your work
You have 10 prompts in your library, each with output and a critique, and you can state one concrete case where GenAI produced a plausible but wrong answer that you caught.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
51

## Slide 52
COURSE ED-TOOLS
Five Collaborative Project Management Tools
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
52

## Slide 53
BROWSER-BASED · REAL-TIME · NO INSTALL
The Ed-Tools You'll Use
1
RACI Collaborative Matrix
Drag A / R / C markers into a live responsibility matrix with your team.
2
Business Model Canvas Studio
The nine-block Osterwalder canvas — validate the business model behind your project.
3
Design Thinking Studio
Empathise, Define, Ideate, Prototype, Test — with dot-voting on ideas.
4
Scrum Agile Transformation Studio
Sprint planning, planning poker, burndown and retrospectives; exports JSON/CSV.
5
Digital AI Transformation Roadmap Studio
Initiatives, impact-vs-effort matrix, 12-month timeline, risk register and KPIs.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
53

## Slide 54
GETTING STARTED
How the Ed-Tools Work
1
One person opens the tool and creates the board or workspace
▶
2
They share the QR code or invite link with the group
▶
3
Everyone joins and types a display name
▶
4
You all edit the same artifact live, in real time
▶
5
Export from Scrum; screenshot the other four as evidence
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
54

## Slide 55
ED-TOOL · USED IN ACTIVITY 5
RACI Collaborative Matrix
Build a responsibility assignment matrix with your team by dragging role markers into a live grid.
https://alfredang.github.io/raci/
Drag A / R / C
Drag markers into cells; click a marker to remove it, or drag to the trash.
Add roles & activities
'+ Add role' and '+ Add activity'; click any header to rename it.
Pre-seeded
A GenAI project example with 4 roles and 5 activities is already loaded.
Share
QR code and board URL — everyone edits the same matrix live.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
55

## Slide 56
ED-TOOL · USED IN ACTIVITY 2
Business Model Canvas Studio
Design and validate the business model behind your project on the nine-block Osterwalder canvas.
https://alfredang.github.io/bcm/
Nine blocks
Partners, Activities, Resources, Value Propositions, Relationships, Channels, Segments, Costs, Revenue.
Sticky notes
Title, description, category, priority — added to any block.
Validate
Set each note Draft → Validate → Confirmed as evidence firms up.
Guidance
The (i) button on each block reveals coaching questions.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
56

## Slide 57
ED-TOOL · USED IN ACTIVITY 6
Design Thinking Studio
Run the five design thinking stages to elicit and prioritise requirements as a group.
https://alfredang.github.io/designthinking/
Five stages
Empathize → Define → Ideate → Prototype → Test.
Empathy map
Says / Thinks / Does / Feels quadrants for your persona.
Dot voting
Voting is enabled on the ideation and prioritisation sections.
Notes
Title, description and category; some sections support resolve.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
57

## Slide 58
ED-TOOL · USED IN ACTIVITY 16
Scrum Agile Transformation Studio
Plan sprints, run ceremonies, estimate with planning poker and hold retrospectives together.
https://alfredang.github.io/scrum/
Pick a role
Product Owner, Scrum Master, Developer, Stakeholder or Agile Coach.
Planning poker
Reveal, reset and commit estimates as a team.
Ceremonies
Sprint planning, burndown tracking and retrospectives.
Exports
JSON, CSV (stories + tasks) or a printable HTML report.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
58

## Slide 59
ED-TOOL · USED IN ACTIVITY 25
Digital AI Transformation Roadmap Studio
Build a transformation roadmap with initiatives, prioritisation, risks and KPIs.
https://alfredang.github.io/digitaltransformation/
Seven tabs
Overview, Phases & Initiatives, Priority Matrix, Maturity, Timeline, Risks, KPIs.
Impact vs Effort
Quick Wins, Major Projects, Fill-ins and Thankless quadrants.
Risk register
Likelihood, impact, computed score, mitigation and owner.
KPIs & timeline
Current vs target values on a 12-month timeline.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
59

## Slide 60
TOPIC 01
Project Initiation and Planning with GenAI
Charter · business case · stakeholders · scope · WBS · schedule · cost
01
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
60

## Slide 61
LO1 · K2, A1
Key Concepts — Topic 01
1
What a project is
A unique product, service or result; time-limited; drives change and enables value creation.
2
GenAI as your planning co-pilot
ChatGPT, Claude, Gemini and Copilot draft charters, WBS, schedules and estimates in minutes — you stay accountable for the judgement.
3
Ten prompting patterns
Persona, Question Refinement, Flipped Interaction, Alternative Approaches, Cognitive Verifier, Fact Check List, Visualisation Generator, Reflection and the risk/decision templates.
4
Project Charter
Authorises the project, names the sponsor and PM, and fixes objectives, budget and success criteria.
5
Business case & value
Cost-benefit analysis and a Business Model Canvas prove economic feasibility before work starts.
6
Scope & requirements
Collect requirements, build the Requirements Traceability Matrix, write the scope statement, decompose into a WBS.
7
Schedule
Define, sequence and estimate activities; build the network diagram and find the critical path.
8
Cost
Analogous, parametric, bottom-up and three-point estimating; the cost baseline plus contingency and management reserves.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
61

## Slide 62
WHAT YOU'LL DO
GenAI Activities — Topic 01
Activities 1–4
• Prompting Patterns for Project Managers
• Business Case and Cost-Benefit Analysis with GenAI
• Develop the Project Charter with GenAI
• Identify and Map Stakeholders with GenAI
Activities 5–8
• Assign Responsibilities with the RACI Ed-Tool
• Collect Requirements with GenAI and Design Thinking
• Build the Requirements Traceability Matrix with GenAI
• Decompose Scope into a WBS and WBS Dictionary with GenAI
Activities 9–10
• Build the Schedule and Find the Critical Path with GenAI
• Estimate Costs and Build the Budget with GenAI
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
62

## Slide 63
INITIATION
Develop the Project Charter
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
63

## Slide 64
HOW IT FITS TOGETHER
Project Integration Management
1
Business case first
A well-researched business case proves the project is worth doing.
2
Then the charter
An approved Project Charter formally authorises the project.
3
Then the plan
A well-planned Project Management Plan integrates scope, schedule, cost and quality.
4
Key benefit
Deliver business value aligned with the organisation's strategic objectives.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
64

## Slide 65
SIX SOURCES OF VALUE
Business Value — Why Projects Are Approved
1
Financial gain
2
New customers
3
Social benefit
4
First to market
5
Improvement — technological or process
6
Regularisation — compliance with standards and regulations
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
65

## Slide 66
PROVING IT'S WORTH DOING
The Business Case
• A documented economic feasibility study that establishes the benefits of the project work.
• It provides the basis for authorisation of further project activities.
• Cost-benefit analysis quantifies the costs against the expected benefits over time.
• The Business Model Canvas tests whether the value proposition and the economics hold together.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
66

## Slide 67
TOPIC 01 · ACTIVITY 2
Business Case and Cost-Benefit Analysis with GenAI
ACTIVITY 2
Before a project is authorised somebody has to prove it is worth doing. You will use GenAI to draft a cost-benefit analysis and a one-page business case, then validate the business model behind it on the Business Model Canvas Studio.
You'll produce
A completed cost-benefit analysis, a one-page business case, and a validated 9-block Business Model Canvas.
Tools: GenAI tool · Business Model Canvas Studio (alfredang.github.io/bcm) · Cost Benefit Analysis.xlsx · Business Case on a Page.docx
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
67

## Slide 68
TOPIC 01 · ACTIVITY 2
Business Case and Cost-Benefit Analysis with GenAI
ACTIVITY 2
PROMPT GenAI WITH
List the one-off and recurring costs, and the quantified annual benefits, of [your project] over 3 years. Present the result as a table with a column explaining how each figure will be verified.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
68

## Slide 69
ACTIVITY 2 · CHECK YOUR WORK
Business Case and Cost-Benefit Analysis with GenAI
✅ Check your work
Your canvas has all nine blocks populated, every note carries a Draft/Validate/Confirmed status, and your business case states a payback period you can defend with your own figures.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
69

## Slide 70
WHAT IT DOES
The Project Charter
1
Authorises the project
It is what allows the project to formally begin.
2
Empowers the PM
It gives the project manager the right to apply organisational resources.
3
Defines the rationale
It states the business need the project answers.
4
Verifies alignment
It confirms the project supports the organisation's strategic goals.
5
Creates focus
It keeps everyone aligned to a single, clear project vision.
6
Is signed
An unsigned charter is not a charter.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
70

## Slide 71
THE REQUIRED CONTENTS
What's Included in a Project Charter
1
Names
Project sponsor, project manager and key stakeholders.
2
Project description
Preliminary requirements and measurable objectives.
3
Business need
Including financial goals and milestones.
4
Summary schedule
High-level milestones.
5
Assumptions & constraints
Boundaries, overall risk, approval requirements, approved budget.
6
From the business case
Success criteria and exit criteria.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
71

## Slide 72
SETTING DIRECTION
Project Vision Statement
• Created by the project sponsor or an executive.
• Includes a clear vision of the desired objectives and how they align with the organisation's strategic goals.
• Refer back to it throughout the project to maintain alignment when pressure to change mounts.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
72

## Slide 73
TOPIC 01 · ACTIVITY 3
Develop the Project Charter with GenAI
ACTIVITY 3
The charter authorises the project and gives the PM the right to apply resources. You will generate a full charter with GenAI and then correct it against what a charter must actually contain.
You'll produce
An approved-quality Project Charter for your group's project.
Tools: GenAI tool · Project Manager Buddy GPT · Project Charter Template.xlsx
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
73

## Slide 74
TOPIC 01 · ACTIVITY 3
Develop the Project Charter with GenAI
ACTIVITY 3
PROMPT GenAI WITH
Write a project charter for launching an internal knowledge-sharing platform. Include objectives, scope, risks, stakeholders and success criteria. Mark every assumption clearly.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
74

## Slide 75
ACTIVITY 3 · CHECK YOUR WORK
Develop the Project Charter with GenAI
✅ Check your work
Your charter names a sponsor and PM, has measurable objectives and explicit success AND exit criteria, and contains no unmarked AI-invented figures.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
75

## Slide 76
STARTING WELL
The Kickoff Meeting
Purpose
• Establish project context
• Assist in team formation
• Align team and stakeholders with the vision
Organisational / Public
• Announce project initiation
• Share the high-level vision, purpose and value
• Identify sponsor, key stakeholders and PM
• Cover high-level charter items
Internal / Team
• Give a charter overview
• Clarify roles and responsibilities
• Present planning results
• Initiate the product backlog
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
76

## Slide 77
PLANNING
The Project Management Plan
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
77

## Slide 78
THE MASTER PLAN
Planning Starts with the Project Management Plan
1
Enables the PM
To execute, monitor, control and close the project.
2
Establishes guardrails
So controls are maintained as the project runs.
3
Allows tailoring
Teams can adapt their way of working and act quickly and flexibly.
4
Integrates everything
Scope, schedule, cost, quality, resource, communications, risk, procurement and stakeholders.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
78

## Slide 79
THE SIX PLANNING DOMAINS
What You Plan
1
Scope — what is and is not included
2
Schedule — when the work happens
3
Resources — who and what is needed
4
Budget — what it will cost
5
Risks — what could go wrong or right
6
Quality — how good it must be
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
79

## Slide 80
TWO PLANNING TECHNIQUES
Collaborative and Rolling Wave Planning
Plan with the team
Plan progressively
• Collaborative planning
– The product owner decides objectives per customer needs
– The team executes the work and helps plan it
– Team members are the local domain experts
– The PM / scrum master helps the team focus
• Rolling wave planning
– A form of progressive elaboration
– Plan near-term work in detail, later work at a high level
– Applied to work packages, planning packages and releases
– Used in both adaptive and predictive approaches
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
80

## Slide 81
STAKEHOLDERS
Identify and Engage Stakeholders
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
81

## Slide 82
DEFINITION
Who is a Stakeholder?
• A stakeholder is anyone affected by your project — or who believes they are affected.
• The outcome you want: productive relationships that ensure stakeholders support the project objectives.
• The process: Identify → Analyse → Prioritise → Engage → Monitor.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
82

## Slide 83
WHO TO LOOK FOR
Project Stakeholders
1
End users
2
Customers
3
Employees
4
The organisation itself
5
Managers
6
Sponsors
7
Business partners
8
Suppliers and contractors
9
Government and regulators
10
The community
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
83

## Slide 84
WHAT YOU RECORD
The Stakeholder Register
1
Name
Who they are.
2
Role
Their role on or around the project.
3
Power / Interest / Influence
How much they can affect the project, and how much they care.
4
Expectations and needs
What they want from the project.
5
Communication requirements
What they need to know, how and how often.
6
Engagement level
Unaware, Resistant, Neutral, Supportive or Leading.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
84

## Slide 85
FOUR REPRESENTATIONS
Analysing Stakeholders
1
2D grids
Power/Interest, Power/Influence, Impact/Influence.
2
3D grid
The stakeholder 'cube'.
3
Salience model
Power, Legitimacy and Urgency combined.
4
Directions of influence
Upward, Downward, Sideward, Outward.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
85

## Slide 86
WHO YOU MUST INFLUENCE
Directions of Influence
1
Upward
Senior management, the sponsor, the steering committee.
2
Downward
The project team and specialists providing knowledge and skills.
3
Sideward
Peers of the PM — other managers competing for the same resources.
4
Outward
Suppliers, users, government departments and the public.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
86

## Slide 87
TOPIC 01 · ACTIVITY 4
Identify and Map Stakeholders with GenAI
ACTIVITY 4
Projects fail on stakeholders more often than on technology. You will use GenAI to generate a stakeholder register, then map power against interest and decide an engagement strategy for each.
You'll produce
A stakeholder register, a power/interest map and a Stakeholder Engagement Assessment Matrix.
Tools: GenAI tool · Stakeholder Impact Over Influence Matrix.xlsx · Salience Model Template.pptx · Stakeholder Engagement Assessment Matrix.xlsx
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
87

## Slide 88
TOPIC 01 · ACTIVITY 4
Identify and Map Stakeholders with GenAI
ACTIVITY 4
PROMPT GenAI WITH
Identify potential stakeholders and their influence and interest levels for a new city-wide bike-sharing system. Explain the evidence needed to validate each rating.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
88

## Slide 89
ACTIVITY 4 · CHECK YOUR WORK
Identify and Map Stakeholders with GenAI
✅ Check your work
Every stakeholder has a quadrant, a salience category, a current and desired engagement level, and one named action to close the gap.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
89

## Slide 90
MARK C FOR CURRENT, D FOR DESIRED
Stakeholder Engagement Assessment Matrix (SEAM)
1
Unaware
Does not know the project exists or its potential impact.
2
Resistant
Aware, and opposed to the change.
3
Neutral
Aware, but neither supportive nor resistant.
4
Supportive
Aware and supportive of the change.
5
Leading
Actively engaged in making the project succeed.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
90

## Slide 91
WHO DOES WHAT
Allocating Responsibilities
1
Responsibility Assignment Matrix
Shows which team members are responsible for which work packages — most commonly a RACI.
2
Team Charter
Created with the team; establishes values, agreements and operating guidelines.
3
Resource Breakdown Structure
An organisational breakdown of the team showing where everyone fits.
4
Resource Calendars
Show when each resource is actually available, including leave and holidays.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
91

## Slide 92
TOPIC 01 · ACTIVITY 5
Assign Responsibilities with the RACI Ed-Tool
ACTIVITY 5
A RACI matrix ends the 'I thought you were doing it' conversation. You will build one collaboratively in a live browser tool, using GenAI to propose the first pass.
You'll produce
A completed RACI matrix for your project, agreed by the whole group.
Tools: RACI Collaborative Matrix (alfredang.github.io/raci) · GenAI tool
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
92

## Slide 93
TOPIC 01 · ACTIVITY 5
Assign Responsibilities with the RACI Ed-Tool
ACTIVITY 5
PROMPT GenAI WITH
For a project with these activities [paste] and these roles [paste], propose a RACI assignment. Give exactly one Accountable role per activity and explain any ambiguous accountability.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
93

## Slide 94
ACTIVITY 5 · CHECK YOUR WORK
Assign Responsibilities with the RACI Ed-Tool
✅ Check your work
Every activity row has exactly one A, at least one R, and your group can justify each assignment; you have a screenshot saved as evidence.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
94

## Slide 95
SCOPE
Collect Requirements & Define Scope
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
95

## Slide 96
HOW SCOPE WILL BE MANAGED
The Scope Management Plan
1
Prepares the scope statement
Defines the process for producing a detailed project scope statement.
2
Enables the WBS
Establishes how the WBS is created from the scope statement.
3
Maintains the baseline
States how the scope baseline is approved and maintained.
4
Governs acceptance
Specifies how formal acceptance of deliverables is obtained.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
96

## Slide 97
FOUR TECHNIQUES
Scope Planning Techniques
1
Document analysis
Derive requirements from existing documents.
2
Alternatives analysis
Identify options and approaches for executing the work.
3
Product analysis
Ask questions about the product — its use and characteristics.
4
Expert judgment
Draw on those who have done this work before.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
97

## Slide 98
HOW REQUIREMENTS ARE ELICITED
Collect Requirements — Techniques
1
Data gathering
Brainstorming, interviews, focus groups, questionnaires, surveys, benchmarking.
2
Interpersonal & team skills
Nominal group technique, observation, facilitation.
3
Data analysis
Document analysis, alternatives analysis, product analysis.
4
Decision making
Voting, multi-criteria decision analysis.
5
Data representation
Mind mapping, affinity diagram, context diagram, use case diagram.
6
Expert judgment
Subject matter experts who know the domain.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
98

## Slide 99
SIX TECHNIQUES
Ideation & Structuring Techniques
1
Brainstorming
Combines a relaxed, informal approach with lateral thinking to generate many ideas.
2
Affinity diagram
Classifies large numbers of ideas into themed groups for review and analysis.
3
Nominal group technique
Individuals rank shortlisted ideas privately, then scores are tallied.
4
Mind mapping
Consolidates ideas into a single map showing commonality and difference.
5
Context diagram
Shows the system at the centre and its interactions with external entities.
6
Benchmarking
Compares your practices against others to identify and adopt best practice.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
99

## Slide 100
TOPIC 01 · ACTIVITY 6
Collect Requirements with GenAI and Design Thinking
ACTIVITY 6
Requirements gathering is where GenAI earns its keep. You will run brainstorming, affinity clustering and prioritisation — using the Design Thinking Studio to structure the work and dot-vote as a group.
You'll produce
A clustered, prioritised requirements set with a MoSCoW classification.
Tools: Design Thinking Studio (alfredang.github.io/designthinking) · GenAI tool · MoSCoW with Sliders Template.xlsx
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
100

## Slide 101
TOPIC 01 · ACTIVITY 6
Collect Requirements with GenAI and Design Thinking
ACTIVITY 6
PROMPT GenAI WITH
Create three user personas and their top pain points for [your project's users]. Then list 15 to 20 ideas for solving the highest-priority pain point. Mark assumptions that require user research.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
101

## Slide 102
ACTIVITY 6 · CHECK YOUR WORK
Collect Requirements with GenAI and Design Thinking
✅ Check your work
Your workspace has personas, an empathy map, a problem statement, a clustered idea board with vote counts, and a MoSCoW list where you changed at least one AI classification.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
102

## Slide 103
CHOOSING WHAT TO BUILD FIRST
Prioritisation Techniques
Technique
How it works
Best for
MoSCoW
Must have / Should have / Could have / Won't have (for now)
Timeboxed agile delivery; comparing several points of view
Kano Model
Delighters, Satisfiers, Dissatisfiers, Indifferent
Prioritising by what most influences customer satisfaction
Paired Comparison
Rate and rank alternatives by comparing each against the other
A small range of subjective requirements
100 Points Method
Stakeholders distribute 100 points across requirements
Any size group; gives priority to stakeholder decision-making
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
103

## Slide 104
PROVING YOU BUILT THE RIGHT THING
The Requirements Traceability Matrix
1
Traces forward
From each requirement to the deliverable that satisfies it.
2
Traces backward
From each deliverable to the stakeholder need that justified it.
3
Links to tests
Every requirement has an acceptance criterion and a test case.
4
Proves completeness
At closure it proves every approved requirement was delivered.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
104

## Slide 105
TOPIC 01 · ACTIVITY 7
Build the Requirements Traceability Matrix with GenAI
ACTIVITY 7
An RTM proves that what you built is what was asked for. GenAI can populate one quickly, but it will happily invent requirement sources — which is exactly the failure mode an RTM exists to prevent.
You'll produce
A complete Requirements Traceability Matrix with verified sources.
Tools: GenAI tool · Requirements Traceability Matrix.xlsx
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
105

## Slide 106
TOPIC 01 · ACTIVITY 7
Build the Requirements Traceability Matrix with GenAI
ACTIVITY 7
PROMPT GenAI WITH
Generate 5 to 10 sample requirements for a smart-city parking app. Include Requirement ID, Description, Source, Acceptance Criterion and Test Case ID. Flag any requirement that is not testable.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
106

## Slide 107
ACTIVITY 7 · CHECK YOUR WORK
Build the Requirements Traceability Matrix with GenAI
✅ Check your work
Every row traces from a real, named source through to an acceptance criterion and a test case, with no orphan requirements or orphan tests.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
107

## Slide 108
WHAT IT CONTAINS
The Project Scope Statement
1
Scope description — of the project and the product
2
Acceptance criteria
3
The required deliverables
4
Out-of-scope items, stated explicitly for clarity
5
Constraints
6
Assumptions
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
108

## Slide 109
WHAT YOU MEASURE AGAINST
Baselines
1
Scope baseline
The approved scope statement + WBS + WBS dictionary.
2
Schedule baseline
The approved version of the schedule.
3
Cost baseline
The approved time-phased budget.
4
Performance measurement baseline
The integrated scope, schedule and cost baseline you measure performance against.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
109

## Slide 110
CHANGING A BASELINE
The Change Request Process
1
Any stakeholder raises a change request
▶
2
Analyse impacts on scope, schedule and cost
▶
3
Record it in the Change Log
▶
4
Change Control Board approves, defers or rejects
▶
5
Communicate the outcome and update the log
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
110

## Slide 111
SCOPE CREEP vs GOLD PLATING
Two Ways Scope Goes Wrong
Scope Creep
Gold Plating
• Scope Creep
– Scope or features are added that were not planned
– Not approved through change control
– Impacts cost and schedule
– Often arrives as many small 'while you're at it' requests
• Gold Plating
– Delivering extra features the customer never asked for
– Usually well-intentioned — the team adds 'value'
– Consumes budget and schedule for no agreed benefit
– Creates support and quality burden later
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
111

## Slide 112
BUILDING THE WBS
Decomposing Work into the WBS
1
Decomposition
Break the work down with your team from deliverables into the smallest useful unit.
2
Work package
A piece of work small enough to be assigned to one person or team.
3
WBS dictionary
Additional scope information for each work package — usually a matrix.
4
The 100% rule
The children of any node must total all of that node's work, with no overlap.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
112

## Slide 113
THE PLANNING CHAIN
From Scope to Schedule
1
Scope Statement
▶
2
Work Breakdown Structure
▶
3
Work Packages
▶
4
Activity List
▶
5
Project Schedule
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
113

## Slide 114
WHAT EACH ENTRY HOLDS
The WBS Dictionary
1
WBS code identifier
2
Associated schedule activities
3
Resources required to complete the work
4
Cost estimates
5
Quality requirements
6
Acceptance criteria and technical references
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
114

## Slide 115
TOPIC 01 · ACTIVITY 8
Decompose Scope into a WBS and WBS Dictionary with GenAI
ACTIVITY 8
The WBS is the backbone of the plan — everything downstream, schedule and cost, is built from it. GenAI decomposes work quickly; your job is to check the decomposition is complete and mutually exclusive.
You'll produce
A three-level WBS and a WBS Dictionary for your work packages.
Tools: GenAI tool · WBS Template.pptx · WBS Dictionary.xlsx
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
115

## Slide 116
TOPIC 01 · ACTIVITY 8
Decompose Scope into a WBS and WBS Dictionary with GenAI
ACTIVITY 8
PROMPT GenAI WITH
Create a three-level work breakdown structure for implementing an internal knowledge portal for a consulting firm. Make every lowest-level item a deliverable-based work package.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
116

## Slide 117
ACTIVITY 8 · CHECK YOUR WORK
Decompose Scope into a WBS and WBS Dictionary with GenAI
✅ Check your work
Your WBS decomposes to assignable work packages, satisfies the 100% rule, includes PM/testing/training effort, and every dictionary entry has testable acceptance criteria.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
117

## Slide 118
SCHEDULE
Build the Schedule & Find the Critical Path
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
118

## Slide 119
HOW SCHEDULING WILL WORK
The Schedule Management Plan
1
Defines activities
How activities will be defined and progressively elaborated.
2
Names the method and tool
The scheduling methodology and the software used.
3
Sets the format
How the schedule will be presented.
4
Sets control criteria
How the schedule will be developed, controlled and updated during execution.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
119

## Slide 120
FOUR WAYS TO SHOW A SCHEDULE
Schedule Presentation Formats
1
Roadmap
High-level view of direction over time — for executives.
2
Gantt Chart
Bars against a calendar showing activities, durations and overlap.
3
Milestone Chart
Key dates only — no durations.
4
Network Diagram
Activities and their dependencies — this is what reveals the critical path.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
120

## Slide 121
FOUR DEPENDENCY TYPES
Activity Dependency Types
Type
Meaning
What the PM can do
Mandatory
Contractually required or inherent in the nature of the work
Must schedule it — there is no way around this sequence
Discretionary
Established from best practice or a preferred sequence
Can be changed if a better sequence exists or compression is needed
External
Activities performed outside the project team's work
Limited or no control — manage as a risk
Internal
Within project work, contingent on the team's own inputs
Full control
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
121

## Slide 122
ADJUSTING THE SEQUENCE
Leads and Lags
Lead — pull forward
Lag — push back
• Lead
– The amount of time an activity can be brought FORWARD
– Allows a successor to start before the predecessor finishes
– Written as a negative value, e.g. FS – 2 days
• Lag
– The amount of time an activity is DELAYED
– Waiting time between activities — concrete curing, approval periods
– Written as a positive value, e.g. FS + 3 days
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
122

## Slide 123
SIX ESTIMATING TECHNIQUES
Estimating Durations
1
Expert judgement
Ask the people who will actually do the work.
2
Analogous
Use a similar past activity — fast, lower accuracy.
3
Parametric
Use a rate — $55 per metre, 8 hours per test case. Medium effort and accuracy.
4
Bottom-up
Add up the smallest pieces — high effort, high accuracy.
5
Three-point
(O + M + P) / 3 — useful when opinions differ.
6
PERT / Beta
(O + 4M + P) / 6 — weights the most likely estimate.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
123

## Slide 124
ESTIMATING AS A TEAM
Wideband Delphi and Planning Poker
• The people who will do the work estimate the effort independently.
• The highest and lowest estimates explain their reasoning to the group.
• Everyone re-estimates. Repeat until the estimates converge.
• Useful in complex situations, and it surfaces hidden assumptions that a single estimate hides.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
124

## Slide 125
THE FOUR TERMS
Schedule Definitions You Must Know
1
Free Float
How long an activity can be delayed without delaying its successor.
2
Total Float
How long an activity can be delayed without delaying the project.
3
Critical Path
The sequence of activities that determines the shortest possible project duration.
4
Forward & Backward Pass
The calculation that determines each activity's float.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
125

## Slide 126
THE CRITICAL PATH
Activities on the critical path have zero float.
Delay any one of them and you delay the whole project. This is why you must know which activities are critical — and GenAI's arithmetic on this must be checked.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
126

## Slide 127
TOPIC 01 · ACTIVITY 9
Build the Schedule and Find the Critical Path with GenAI
ACTIVITY 9
You will turn your work packages into a sequenced, estimated schedule, draw the network diagram, and compute the critical path — then check whether GenAI's arithmetic can be trusted.
You'll produce
A Gantt chart, a schedule network diagram and a calculated critical path.
Tools: GenAI tool · Gantt Chart Template.xlsx · Schedule Network Diagram.xlsx
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
127

## Slide 128
TOPIC 01 · ACTIVITY 9
Build the Schedule and Find the Critical Path with GenAI
ACTIVITY 9
PROMPT GenAI WITH
Using the task data provided, propose a project schedule for building a CRM system. Preserve the stated dependencies, identify the critical path and show your forward-pass and backward-pass calculations.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
128

## Slide 129
ACTIVITY 9 · CHECK YOUR WORK
Build the Schedule and Find the Critical Path with GenAI
✅ Check your work
You can state the critical path, the total duration and the float on at least one non-critical activity, and you have checked GenAI's computed path against your own.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
129

## Slide 130
COST
Estimate Costs & Determine the Budget
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
130

## Slide 131
FOUR WAYS TO ESTIMATE
Estimating Costs — Four Techniques
1
Analogous
Use historical information and expert judgement from a previous similar project. Low cost, reasonably accurate.
2
Parametric
Take a rate from historical data and apply it: cost = quantity × rate per unit.
3
Bottom-up
Roll costs up from the smallest activity. Most accurate, but time consuming and costly.
4
Three-point
Ce = (Co + 4Cm + Cp) / 6 — a weighted average that reduces bias and uncertainty.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
131

## Slide 132
TWO FUNDING MODELS
Budgets — Predictive vs Agile
Predictive
Agile
• Predictive projects
– Total budget built bottom-up from work package estimates
– Contingency reserves added for identified risks
– Management reserves added for unforeseen scope
– Once approved, changed only by change request
• Agile projects
– The team is fully funded for a set period
– Cost and time are FIXED
– Scope is the variable — prioritised by the product owner
– Value is delivered incrementally within the funded period
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
132

## Slide 133
PLANNING FOR WHAT YOU DON'T KNOW
Reserves
1
Contingency Reserve
Set aside for identified risks should they occur. Sits INSIDE the cost baseline. Controlled by the PM.
2
Management Reserve
Set aside for unforeseen work within scope. Sits OUTSIDE the cost baseline. Requires management approval.
3
Reserve Analysis
Compares the amount of risk remaining against the amount of contingency remaining.
4
Cost Baseline
All work package costs (bottom-up) plus the contingency reserve.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
133

## Slide 134
TOPIC 01 · ACTIVITY 10
Estimate Costs and Build the Budget with GenAI
ACTIVITY 10
You will apply the four estimating techniques to the same work, compare what each produces, and assemble a cost baseline with contingency and management reserves.
You'll produce
A cost baseline built bottom-up from your WBS, with reserves and a documented estimating basis.
Tools: GenAI tool · Cost Benefit Analysis.xlsx · your WBS from Activity 8
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
134

## Slide 135
TOPIC 01 · ACTIVITY 10
Estimate Costs and Build the Budget with GenAI
ACTIVITY 10
PROMPT GenAI WITH
Estimate the cost of each work package in this WBS using bottom-up estimating. Show assumed rates and quantities separately from totals, then add contingency and management reserves without double counting.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
135

## Slide 136
ACTIVITY 10 · CHECK YOUR WORK
Estimate Costs and Build the Budget with GenAI
✅ Check your work
You have one cost baseline built bottom-up, four comparable estimates for the same work, no unmarked assumed rates, and a stated contingency and management reserve you can justify.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
136

## Slide 137
TOPIC RECAP
Recap — Project Initiation and Planning with GenAI
• Apply structured prompting patterns to produce usable project management output.
• Establish the economic feasibility of a project using GenAI-assisted analysis.
• Develop project parameters with GenAI according to business requirements.
• Identify stakeholders and plan engagement using GenAI-assisted analysis.
• Allocate project responsibilities unambiguously using a responsibility assignment matrix.
• Elicit, structure and prioritise requirements using GenAI-supported techniques.
• Trace every requirement from source through to test and deliverable.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
137

## Slide 138
Lunch Break
1 hour

## Slide 139
TOPIC 02
Project Execution and Delivery with GenAI
Directing work · knowledge · quality · resources · team · communications
02
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
139

## Slide 140
LO2 · K3, A2
Key Concepts — Topic 02
1
Direct and manage project work
Turn the plan into deliverables; distinguish work performance data, information and reports.
2
Manage project knowledge
Capture explicit knowledge and surface tacit knowledge; GenAI summarises lessons learned as you go.
3
Quality management
Cost of quality, PDCA, DMAIC, Kaizen; fishbone, five whys and Pareto for root-cause analysis.
4
Acquire and develop resources
Resource levelling vs smoothing; Tuckman's ladder; motivational theories.
5
Manage the team
Conflict management approaches, emotional intelligence and interpersonal skills.
6
Manage communications
The N(N-1)/2 channel formula, the Five Cs, push vs pull, and barriers to communication.
7
Optimising resources and budget
Use GenAI to model resource and budget options, then justify the trade-off you choose.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
140

## Slide 141
WHAT YOU'LL DO
GenAI Activities — Topic 02
Activities 11–13
• Direct Project Work and Report Performance with GenAI
• Manage Project Knowledge with GenAI
• Root Cause Analysis with GenAI — Fishbone, Five Whys and Pareto
Activities 14–16
• Continuous Improvement with GenAI — PDCA and DMAIC
• Optimise Resources and Budget with GenAI
• Develop and Manage the Team with GenAI
Activities 17–17
• Plan and Manage Communications with GenAI
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
141

## Slide 142
EXECUTION
Direct and Manage Project Work
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
142

## Slide 143
MAKING IT HAPPEN
Directing the Work
1
Implement the plan
Turn the project management plan into actual deliverables.
2
Manage the flow
Keep work moving and remove impediments for the team.
3
Implement approved changes
Only approved changes — everything else goes through change control.
4
Collect the data
Work performance data flows out of the work and into your reporting.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
143

## Slide 144
THE REPORTING CHAIN
Data → Information → Reports
Work Performance DATA
• The raw observations
• '14 defects open'
• 'Actual cost $62,000'
• No meaning on its own
Work Performance INFORMATION
• Comparison of two or more data points
• 'Schedule variance is –$10,000'
• '8 work packages done vs 10 planned'
• Now it means something
Work Performance REPORTS
• The physical or electronic representation
• Status reports, dashboards, memos
• Intended to raise action or awareness
• What the sponsor actually sees
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
144

## Slide 145
KEEPING CONTROL OF THE RECORD
Managing Project Information
1
PMIS
The Project Management Information System gathers, integrates and shares project data.
2
Artifact management
Systems that store and maintain project artifacts.
3
Version control
Every update gets a new version number, a date/time stamp and the name of who changed it.
4
Configuration management
Controls which version of a deliverable is the approved one.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
145

## Slide 146
TOPIC 02 · ACTIVITY 11
Direct Project Work and Report Performance with GenAI
ACTIVITY 11
Executing a project generates a flood of raw data. You will use GenAI to turn that data into information, and information into a report a sponsor will actually read — while learning the distinction that PMBOK draws between the three.
You'll produce
A project status report generated from raw work performance data.
Tools: GenAI tool · Project Manager Buddy GPT
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
146

## Slide 147
TOPIC 02 · ACTIVITY 11
Direct Project Work and Report Performance with GenAI
ACTIVITY 11
PROMPT GenAI WITH
Here is raw work performance data from my project [paste]. Compare it with the plan, distinguish data from interpretation, and produce a one-page status report for an executive sponsor.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
147

## Slide 148
ACTIVITY 11 · CHECK YOUR WORK
Direct Project Work and Report Performance with GenAI
✅ Check your work
Your report distinguishes data from information, every comparison uses a real baseline figure, and it opens with status, biggest problem and the decision required.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
148

## Slide 149
KNOWLEDGE THAT OUTLIVES THE PROJECT
Manage Project Knowledge
1
Explicit knowledge
Documented and easily shared — plans, reports, procedures. Archive it.
2
Tacit knowledge
Held in people's heads — experience, judgement, relationships. Must be surfaced.
3
Curate as an asset
Treat knowledge as an asset to the team and the organisation.
4
Lessons learned
Captured continuously through the project, not only at the end.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
149

## Slide 150
TOPIC 02 · ACTIVITY 12
Manage Project Knowledge with GenAI
ACTIVITY 12
Knowledge that lives only in people's heads leaves when they do. You will use GenAI to turn messy project conversations into a structured, searchable knowledge asset and a lessons-learned register.
You'll produce
A lessons-learned register and a knowledge asset entry for your project.
Tools: GenAI tool · Claude (long-document handling)
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
150

## Slide 151
TOPIC 02 · ACTIVITY 12
Manage Project Knowledge with GenAI
ACTIVITY 12
PROMPT GenAI WITH
From these project records [paste], extract decisions and owners, open questions, lessons learned, and tacit knowledge that is implied but not stated. Quote the evidence used for each extraction.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
151

## Slide 152
ACTIVITY 12 · CHECK YOUR WORK
Manage Project Knowledge with GenAI
✅ Check your work
Your register has actionable lessons with root causes, at least one item of genuinely tacit knowledge surfaced, and your group can state your organisation's data-confidentiality limits.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
152

## Slide 153
QUALITY
Manage and Control Quality
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
153

## Slide 154
TWO APPROACHES
Quality in Predictive vs Agile Projects
Predictive
Agile
• Predictive
– Product is developed, then tested
– Testing happens in sequence, usually in large batches
– Quality assurance is often a separate function
• Agile
– Quality is everyone's responsibility
– Correct requirements and acceptance criteria up front
– Simple design and regular refactoring
– Test-first: write the test, then the code that passes it
– Small deliverable demonstrated in the sprint review
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
154

## Slide 155
WHY QUALITY IS PLANNED, NOT INSPECTED IN
Quality is more expensive to fix the closer it gets to your customer.
A defect caught in design costs almost nothing. The same defect caught by a customer costs you rework, reputation and trust.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
155

## Slide 156
FOUR COST CATEGORIES
The Cost of Quality
1
Prevention costs
Preventing future defects — training, prototypes, refactoring, good design.
2
Appraisal costs
Finding defects — testing, quality audits, inspections, the sprint review.
3
Internal failure
The product fails internally, usually during testing or review.
4
External failure
Non-conformance reaches the customer — complaints, returns, reputational damage.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
156

## Slide 157
FOUR IMPROVEMENT FRAMEWORKS
Quality Methods for Continuous Improvement
1
Six Sigma / DMAIC
Define, Measure, Analyse, Improve, Control — focused on removing variation and waste.
2
Kaizen
'Change for better' — continuous small improvements by everyone.
3
PDCA
Plan-Do-Check-Act — the Shewhart / Deming cycle.
4
Agile methods
Scrum, Kanban and their built-in inspect-and-adapt loops.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
157

## Slide 158
FINDING THE REAL CAUSE
Root Cause Analysis Tools
1
Ishikawa / Fishbone
Cause-and-effect diagram grouping causes into categories.
2
The Five Whys
Ask 'why' repeatedly until you reach something you can actually change.
3
Pareto Chart
The 80/20 rule — find the vital few causes creating most of the problem.
4
Six Thinking Hats
Examine the problem deliberately from six different perspectives.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
158

## Slide 159
TOPIC 02 · ACTIVITY 13
Root Cause Analysis with GenAI — Fishbone, Five Whys and Pareto
ACTIVITY 13
When delivery goes wrong, the visible problem is rarely the real one. You will run three complementary root-cause techniques on the same problem with GenAI's help and compare what each reveals.
You'll produce
A fishbone diagram, a five-whys chain and a Pareto analysis of the same delivery problem.
Tools: GenAI tool · Fishbone Diagram Template.pptx · Pareto Principle Template.xlsx
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
159

## Slide 160
TOPIC 02 · ACTIVITY 13
Root Cause Analysis with GenAI — Fishbone, Five Whys and Pareto
ACTIVITY 13
PROMPT GenAI WITH
Analyse the issue records provided and identify the most likely root causes of recurring project deadline misses. Produce a fishbone structure, a five-whys chain and a Pareto-ready category table without inventing evidence.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
160

## Slide 161
ACTIVITY 13 · CHECK YOUR WORK
Root Cause Analysis with GenAI — Fishbone, Five Whys and Pareto
✅ Check your work
You have all three artifacts for one problem, you added at least two organisation-specific causes the AI missed, and your five-whys chain ends at something you can change.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
161

## Slide 162
CONTINUOUS IMPROVEMENT
PDCA — The Deming Cycle
1
PLAN — review real data, find the root cause, prioritise solutions with the team
▶
2
DO — put the plan into action as a pilot in a small area first
▶
3
CHECK — check the results against a specific measure
▶
4
ACT — adjust: standardise if it worked, or try again if it did not
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
162

## Slide 163
STRUCTURED PROBLEM SOLVING
DMAIC — Six Sigma
1
DEFINE the problem as a gap between where you are and where you want to be
▶
2
MEASURE the current problem with real data
▶
3
ANALYSE the data and find the root cause
▶
4
IMPROVE — put the plan into action and measure the result
▶
5
CONTROL — ensure the new process stays in control
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
163

## Slide 164
TOPIC 02 · ACTIVITY 14
Continuous Improvement with GenAI — PDCA and DMAIC
ACTIVITY 14
Having found a root cause, you need a disciplined way to fix it and make the fix stick. You will run the same improvement through both PDCA and DMAIC and see where they differ.
You'll produce
A completed PDCA cycle and a DMAIC project definition for your improvement.
Tools: GenAI tool · Plan Do Check Act.pptx · DMAIC.pptx
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
164

## Slide 165
TOPIC 02 · ACTIVITY 14
Continuous Improvement with GenAI — PDCA and DMAIC
ACTIVITY 14
PROMPT GenAI WITH
Design a PDCA cycle to address [root cause]. For Plan, state the evidence and prioritised solution; for Do, define a small pilot; for Check, define the success measure; for Act, state what happens if the pilot succeeds or fails.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
165

## Slide 166
ACTIVITY 14 · CHECK YOUR WORK
Continuous Improvement with GenAI — PDCA and DMAIC
✅ Check your work
Your Check/Control stages specify a number and a date, your Do stage is a pilot, and you can justify choosing PDCA or DMAIC for this problem.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
166

## Slide 167
MEETING EXTERNAL REQUIREMENTS
Compliance Requirements
1
Know the standards
Government regulations, organisational policies, product and project quality requirements.
2
Classify
Determine which compliance categories apply to your project.
3
Assess threats
Determine potential threats to compliance and analyse the consequences of non-compliance.
4
Act
Determine the necessary approach and actions to address compliance needs.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
167

## Slide 168
RESOURCES
Acquire, Develop and Manage Resources
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
168

## Slide 169
PLANNING THE PEOPLE AND THE KIT
The Resource Management Plan
1
Identify resources
Both people and physical resources, and how to acquire them.
2
Roles and responsibilities
Role (function), Authority (rights to decide and use resources), Responsibility (assigned duty).
3
Competencies
The skills required, and the training strategy to close any gaps.
4
Organisation chart
A visual showing resource categories and reporting relationships.
5
Resource controls
Ensuring non-human resources are available when needed.
6
Recognition plan
How contribution will be recognised and rewarded.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
169

## Slide 170
TWO TECHNIQUES — KNOW THE DIFFERENCE
Resource Optimisation
Levelling
Smoothing
• Resource Levelling
– Used when a shared resource is over-allocated
– Or assigned to two or more activities in the same period
– Adjusts the schedule to resolve it
– MAY change the critical path and the end date
• Resource Smoothing
– Adjusts activities only within their free and total float
– The critical path is NOT changed
– The end date is preserved
– May not fully resolve the over-allocation
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
170

## Slide 171
WHEN YOU MUST GO FASTER
Schedule Compression
Crashing — spend money
Fast tracking — take risk
• Crashing
– Add resources to shorten duration for least incremental cost
– Overtime, extra people, paying to expedite
– ONLY works on critical path activities
– Increases cost, and often risk
• Fast Tracking
– Perform activities in parallel that were planned in sequence
– Overlaps critical path activities to shorten duration
– No additional cost up front
– Increases risk of rework — which can cost more later
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
171

## Slide 172
TOPIC 02 · ACTIVITY 15
Optimise Resources and Budget with GenAI
ACTIVITY 15
This is the heart of LO2. A resource is over-allocated and the budget is under pressure — you will use GenAI to generate genuine alternatives, evaluate the trade-offs, and defend the option you choose.
You'll produce
A resource optimisation decision with a documented trade-off analysis.
Tools: GenAI tool · your schedule from Activity 9 · Gantt Chart Template.xlsx
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
172

## Slide 173
TOPIC 02 · ACTIVITY 15
Optimise Resources and Budget with GenAI
ACTIVITY 15
PROMPT GenAI WITH
I have an over-allocated resource on these activities [paste] and a 15% budget reduction. Compare resource levelling, resource smoothing, crashing and fast tracking, including cost, schedule, quality and risk trade-offs.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
173

## Slide 174
ACTIVITY 15 · CHECK YOUR WORK
Optimise Resources and Budget with GenAI
✅ Check your work
Your chosen option is correctly named, crashing (if used) targets the critical path, and you can justify the cost/schedule/risk trade-off in three sentences.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
174

## Slide 175
TEAM
Develop and Manage the Project Team
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
175

## Slide 176
AN EFFECTIVE TEAM IS THE KEY TO SUCCESS
“
Of all the things I've done, the most vital is coordinating the talents of those who work for us and pointing them toward a certain goal.
Walt Disney
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
176

## Slide 177
HOW TEAMS DEVELOP
Tuckman's Ladder
1
FORMING — members come together, still independent and individual
▶
2
STORMING — conflict arises as personalities and working styles meet
▶
3
NORMING — the team learns each other's roles and finds a rhythm
▶
4
PERFORMING — high trust, the team relies on each other
▶
5
ADJOURNING — the project finishes and the team moves on
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
177

## Slide 178
BUILDING THE TEAM
Team Building
1
Cohesion drives performance
Cohesion and solidarity help teams perform better.
2
Leadership facilitates it
Good leadership helps bonding between team members.
3
Builds trust and empathy
Activities build unity, trust and focus on the team over the individual.
4
Formal or informal
Brief or extended, facilitated by you or by a professional.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
178

## Slide 179
WHAT MOTIVATES YOUR TEAM
Motivational Theories
1
Maslow's Hierarchy of Needs
Physiological, safety, belonging, esteem, self-actualisation — lower needs first.
2
Herzberg's Motivation-Hygiene
Hygiene factors prevent dissatisfaction; motivators create satisfaction.
3
McGregor's Theory X and Y
X: people avoid work and need direction. Y: people take pride in work and need trust.
4
McClelland's Achievement Motivation
Needs for achievement, affiliation or power — one becomes dominant.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
179

## Slide 180
CONFLICT IS NORMAL
Conflict Management
1
Everyone's responsibility
All team members and stakeholders are responsible for managing conflict.
2
The PM influences it
Through interpersonal skills and servant leadership.
3
The team is empowered
To resolve conflicts themselves; the lead facilitates resolution.
4
Conflict is not all bad
Disruption and innovation are connected — encourage exchange and disagreement, prevent escalation.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
180

## Slide 181
WHERE IT COMES FROM
Causes of Conflict
1
Competition for scarce resources
2
Differences in objectives, values and perceptions
3
Disagreements about roles and work activities
4
Communication breakdowns
5
Projects are unique — the team has not worked together before
6
Ambiguous accountability
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
181

## Slide 182
CHOOSING YOUR APPROACH
Five Conflict Management Approaches
Approach
What it means
When to use it
Collaborate / Problem Solve
Win/Win — incorporate multiple viewpoints, seek consensus
When you need commitment and have time; the ideal default
Compromise / Reconcile
Lose/Lose — each side gives something up
When both parties have equal power and time is short
Smooth / Accommodate
Lose/Win — emphasise agreement, concede your position
When the relationship matters more than the issue
Force / Direct
Win/Lose — pursue your view at others' expense
In an emergency, or on safety and deadline-critical decisions
Withdraw / Avoid
Retreat and postpone the issue
When the issue is trivial, or emotions need to cool first
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
182

## Slide 183
THE PM'S MOST USEFUL SKILL
Emotional Intelligence
1
Self-Awareness
Understanding how your actions affect others.
2
Self-Management
Thinking before you act.
3
Social Awareness
Being empathetic to those around you.
4
Social Skill
Establishing rapport and managing your own attitude.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
183

## Slide 184
TOPIC 02 · ACTIVITY 16
Develop and Manage the Team with GenAI
ACTIVITY 16
Delivery problems are usually people problems. You will use GenAI to prepare for a difficult conversation and to select a conflict management approach — while judging where AI advice on people is genuinely useful and where it is not.
You'll produce
A prepared difficult conversation and a team development plan mapped to Tuckman's stages.
Tools: GenAI tool · Claude · Scrum Agile Transformation Studio (alfredang.github.io/scrum)
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
184

## Slide 185
TOPIC 02 · ACTIVITY 16
Develop and Manage the Team with GenAI
ACTIVITY 16
PROMPT GenAI WITH
My project team is in the [stage] stage of Tuckman's model and showing these behaviours [paste]. Recommend leadership actions that can move the team forward, and explain which observations support each action.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
185

## Slide 186
ACTIVITY 16 · CHECK YOUR WORK
Develop and Manage the Team with GenAI
✅ Check your work
You have a conversation plan you would actually use, a named conflict approach with justification, an exported retrospective file, and a clear line on what not to delegate to AI.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
186

## Slide 187
COMMUNICATIONS
Plan and Manage Communications
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
187

## Slide 188
THE COMMUNICATION CHANNEL FORMULA
N × (N – 1) ÷ 2
A team of 10 people has 45 communication channels. A team of 15 has 105. Communication complexity grows faster than the team.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
188

## Slide 189
WHAT THE PLAN SPECIFIES
The Communications Management Plan
1
Who
Senders, receivers, and who authorises confidential information.
2
What
The type of information and the reason for communicating it.
3
How
Language, format, content and level of detail.
4
When
Time frame and frequency; whether acknowledgment is required.
5
Escalation
The process and guidance for escalating issues.
6
Resources
Methods and technologies used, plus allocated time and budget.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
189

## Slide 190
WRITING THAT WORKS
The Five Cs of Communication
1
Correct
Correct grammar and spelling — errors undermine your credibility.
2
Concise
Eliminate excess words. Respect the reader's time.
3
Clear
A clear purpose, directed at the needs of the reader.
4
Coherent
A logical flow of ideas.
5
Controlling
Control the flow of words and ideas — lead with what matters.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
190

## Slide 191
TWO COMMUNICATION METHODS
Push vs Pull Communication
Push
Pull
• Push
– Sent directly to specific recipients
– Emails, reports, memos, voicemails
– Ensures it was DISTRIBUTED — not that it was understood
– Use for what must be read
• Pull
– Recipients access it at their own discretion
– Intranet sites, dashboards, knowledge repositories
– Suits large volumes and large audiences
– Use for reference information
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
191

## Slide 192
SIX SKILLS
Communication Skills
1
Active listening
Stay engaged, show interest, summarise back to check understanding.
2
Feedback
Written, verbal or non-verbal — ensures the message was heard correctly.
3
Non-verbal
Body language, gestures, tone of voice, facial expressions.
4
Presentations
Formal delivery of progress and updates to stakeholders.
5
Cultural awareness
Habits, priorities, celebrations and ways of working differ.
6
Managing expectations
Set expectations early; negotiate to manage them continuously.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
192

## Slide 193
WHAT GETS IN THE WAY
Barriers to Communication
1
Language differences
2
Cultural differences
3
Physical barriers — noise, distance, poor infrastructure
4
Psychological barriers — stress, emotion
5
Perceptual barriers — different interpretations
6
Information overload
7
Jargon and technical language
8
Attitudes, prejudices and poor listening
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
193

## Slide 194
RECOGNISING STYLES IN YOUR TEAM
Communication Styles
1
Assertive
Direct, respectful and confident — the style to aim for.
2
Aggressive
Dominating, confrontational and disrespectful.
3
Passive
Submissive, avoids confrontation, indirect.
4
Passive-aggressive
Indirect, with disguised hostility.
5
Manipulative
Controlling and deceitful, using influence to achieve hidden goals.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
194

## Slide 195
TOPIC 02 · ACTIVITY 17
Plan and Manage Communications with GenAI
ACTIVITY 17
You will calculate how communication complexity grows, then use GenAI to build a communications plan and adapt a single message for very different audiences.
You'll produce
A communications management plan and the same update written for three audiences.
Tools: GenAI tool · your stakeholder register from Activity 4
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
195

## Slide 196
TOPIC 02 · ACTIVITY 17
Plan and Manage Communications with GenAI
ACTIVITY 17
PROMPT GenAI WITH
Build a communications management plan from the stakeholder data provided. For each stakeholder specify information needed, purpose, format, level of detail, frequency, channel and sender.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
196

## Slide 197
ACTIVITY 17 · CHECK YOUR WORK
Plan and Manage Communications with GenAI
✅ Check your work
Your plan gives each stakeholder a specific frequency and channel, uses push and pull deliberately, and your three message versions genuinely differ in what they lead with.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
197

## Slide 198
TOPIC RECAP
Recap — Project Execution and Delivery with GenAI
• Turn raw project data into work performance information and reports.
• Capture explicit and tacit knowledge so it is reusable by the organisation.
• Diagnose the root cause of a delivery problem, not just its symptoms.
• Structure an improvement cycle and control the result.
• Resolve over-allocation and budget pressure by modelling options with GenAI (K3).
• Advise staff in resolving challenges during project delivery (A2).
• Build a communications plan that matches each stakeholder's real needs.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
198

## Slide 199
Tea Break
15 minutes

## Slide 200
TOPIC 03
Managing Project Risks with GenAI
Risk · procurement · monitoring & control · earned value · closure
03
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
200

## Slide 201
LO3 · K1, A3, A4
Key Concepts — Topic 03
1
Risk vs issue
Risks are future and may be positive or negative (risk register); issues are present and always negative (issue log).
2
Identify and analyse risk
RBS, brainstorming, SWOT and the Delphi technique; qualitative probability/impact then quantitative analysis.
3
Quantitative analysis
Sensitivity (tornado) charts and decision-tree expected monetary value.
4
Plan risk responses
Avoid, transfer, mitigate, accept — escalate, exploit, share, enhance; secondary and residual risk.
5
Procurement
RFI/RFP/RFQ, contract types, claims and alternative dispute resolution.
6
Monitor and control
Integrated change control, validate and control scope, schedule and cost.
7
Earned value analysis
PV, EV, AC; CV, SV, CPI, SPI; EAC and ETC forecasting.
8
Control quality & close
Check sheets, control charts and the rule of seven; then close the project and capture lessons learned.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
201

## Slide 202
WHAT YOU'LL DO
GenAI Activities — Topic 03
Activities 18–20
• Identify Project Risks with GenAI
• Qualitative Risk Analysis with GenAI
• Quantitative Risk Analysis with GenAI — Tornado Charts and Decision Trees
Activities 21–23
• Plan Risk Responses with GenAI
• Plan Procurement and Manage Contracts with GenAI
• Earned Value Analysis with GenAI
Activities 24–25
• Control Quality with GenAI — Check Sheets and Control Charts
• Monitor, Control Change and Close the Project with GenAI
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
202

## Slide 203
RISK
Identify and Analyse Project Risks
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
203

## Slide 204
DEFINITION
What is Project Risk?
1
Known and unknown causes
Risk originates inside and outside the business environment.
2
Signalled by a trigger
A trigger condition indicates the risk is developing.
3
Positive or negative
Risks can be opportunities as well as threats.
4
Becomes an issue
If a risk materialises it becomes an issue, and you must act.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
204

## Slide 205
A DISTINCTION THAT MATTERS
Risks vs Issues
Risk
Issue
• RISKS
– Focused on the FUTURE
– Can be positive or negative
– Documented in the RISK REGISTER
– The response is called a 'risk response'
– You plan for them in advance
• ISSUES
– Focused on the PRESENT
– Always negative
– Documented in the ISSUE LOG
– The response is called a 'workaround'
– You deal with them now
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
205

## Slide 206
WHY YOU PLAN FOR RISK
Risk, like quality, is cheaper to fix early.
A risk identified in planning can be designed out. The same risk discovered in execution costs you schedule, budget and credibility.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
206

## Slide 207
SIX TECHNIQUES
Risk Identification Techniques
1
Risk Breakdown Structure
A hierarchy of risk categories used as a checklist when brainstorming.
2
Brainstorming
Generate risks freely with the team before filtering.
3
Nominal group technique
Individuals rank risks privately, then scores are tallied.
4
SWOT analysis
Strengths, Weaknesses, Opportunities, Threats.
5
Assumption analysis
Every assumption in the plan is a risk if it proves false.
6
Delphi technique
Anonymous expert input, iterated until consensus emerges.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
207

## Slide 208
WHERE TO LOOK
Common Types of Project Risk
1
Budget, cost and exchange rate
2
Schedule and project dependencies
3
Scope creep and requirement risk
4
Technology, design and architecture
5
Supplier, procurement and contract
6
Regulatory, legal and compliance
7
Resource, skill and sponsor support
8
Quality, security and reputation
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
208

## Slide 209
CAUSE → EVENT → EFFECT
Writing a Proper Risk Statement
• A risk is not a single word. 'Vendor' is not a risk.
• Use the structure: CAUSE → RISK EVENT → EFFECT.
• 'Because the vendor has only one integration engineer, their resource may be unavailable in December, delaying UAT by two weeks.'
• Now it is specific enough to assign an owner, a trigger and a response.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
209

## Slide 210
TOPIC 03 · ACTIVITY 18
Identify Project Risks with GenAI
ACTIVITY 18
GenAI is genuinely excellent at risk identification — it will suggest risks your team would never think of. It is correspondingly poor at knowing which of them matter to you. You will use both facts.
You'll produce
A populated risk register with risks sourced from GenAI and from your team.
Tools: GenAI tool · Project Manager Buddy GPT · Risk Register template
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
210

## Slide 211
TOPIC 03 · ACTIVITY 18
Identify Project Risks with GenAI
ACTIVITY 18
PROMPT GenAI WITH
Act as an expert project manager in the [industry] working on a [project type]. Use the supplied project facts to draft a risk register covering cause, event, effect, category, owner and evidence. Separate facts from assumptions.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
211

## Slide 212
ACTIVITY 18 · CHECK YOUR WORK
Identify Project Risks with GenAI
✅ Check your work
Your register has risks from both sources, every entry is written as cause → event → effect with an owner, and you can name one risk your team found that the AI missed.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
212

## Slide 213
PRIORITISING RISK
Qualitative Risk Analysis
1
Do it first
Subjective assessment comes before any quantitative work.
2
Probability × Impact
Combine the probability of occurrence with the impact if it occurs.
3
Prioritise
The output is a prioritised shortlist, not a score for every risk.
4
Then quantify
Move to quantitative analysis only if further support is required.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
213

## Slide 214
BEYOND PROBABILITY AND IMPACT
Other Risk Factors
1
Urgency
How soon a response is needed to be effective.
2
Proximity
How close the risk is to occurring.
3
Dormancy
The period between the risk occurring and you discovering it.
4
Manageability
How easily the risk can be managed if it occurs.
5
Controllability
How easily the risk outcome can be controlled.
6
Strategic impact
How the risk affects the organisation's goals.
7
Connectivity
How related this risk is to other project risks.
8
Propinquity
The degree to which stakeholders actually care about the risk.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
214

## Slide 215
YOUR RISK RECORD
The Risk Register
1
Risk ID and title
2
Category and description (cause → event → effect)
3
Probability, impact and score
4
Risk owner
5
Planned response and trigger condition
6
Current status and residual risk
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
215

## Slide 216
TOPIC 03 · ACTIVITY 19
Qualitative Risk Analysis with GenAI
ACTIVITY 19
You cannot act on fifty risks. Qualitative analysis prioritises them so you spend your attention where it matters — and you will test how consistent GenAI's scoring actually is.
You'll produce
A scored probability/impact matrix with a prioritised risk shortlist.
Tools: GenAI tool · Probability and Impact Matrix template
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
216

## Slide 217
TOPIC 03 · ACTIVITY 19
Qualitative Risk Analysis with GenAI
ACTIVITY 19
PROMPT GenAI WITH
Score each supplied risk for probability and impact from 1 to 5, calculate the risk score, place it in a probability-impact matrix and explain any score that is not directly supported by the data.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
217

## Slide 218
ACTIVITY 19 · CHECK YOUR WORK
Qualitative Risk Analysis with GenAI
✅ Check your work
Your top ten risks have group-agreed scores, your top five carry proximity and dormancy assessments, and you can explain why AI scoring alone is not sufficient.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
218

## Slide 219
PUTTING NUMBERS ON RISK
Quantitative Risk Analysis
Tornado charts
Decision trees
• Sensitivity Analysis / Tornado Chart
– Shows which variables most affect the outcome
– Each bar is a variable's high-to-low impact range
– Longest bars at the top — those are your priorities
– Tells you where to focus management attention
• Decision Tree Analysis
– Shows decisions, outcomes and their probabilities
– Each path carries a cost and a payoff
– Produces an Expected Monetary Value per branch
– EMV = Σ (probability × payoff) – branch cost
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
219

## Slide 220
TOPIC 03 · ACTIVITY 20
Quantitative Risk Analysis with GenAI — Tornado Charts and Decision Trees
ACTIVITY 20
When a decision carries real money, qualitative scoring is not enough. You will run a sensitivity analysis and a decision tree, using GenAI for the setup and doing the arithmetic yourself.
You'll produce
A tornado chart identifying your most sensitive risk variables and a decision tree with expected monetary values.
Tools: GenAI tool · Tornado Chart - Sensitivity Analysis.xlsx · Decision Tree Analysis.xlsx
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
220

## Slide 221
TOPIC 03 · ACTIVITY 20
Quantitative Risk Analysis with GenAI — Tornado Charts and Decision Trees
ACTIVITY 20
PROMPT GenAI WITH
Use the supplied high, base and low values to rank the ten variables by their effect on project cost or schedule. Produce tornado-chart data and one decision tree with expected monetary values, showing every calculation.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
221

## Slide 222
ACTIVITY 20 · CHECK YOUR WORK
Quantitative Risk Analysis with GenAI — Tornado Charts and Decision Trees
✅ Check your work
Your tornado chart is ordered by sensitivity with justified asymmetric ranges, and you have hand-verified the EMV of every decision tree branch.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
222

## Slide 223
EIGHT STRATEGIES · ESCALATE APPLIES TO BOTH
Risk Response Strategies
Threats
Opportunities
• For THREATS (negative risk)
– AVOID — eliminate the cause; change the plan
– TRANSFER — shift the impact to a third party (insurance, contract)
– MITIGATE — reduce the probability or the impact
– ACCEPT — take no action; hold a contingency reserve
• For OPPORTUNITIES (positive risk)
– EXPLOIT — make certain the opportunity happens
– SHARE — partner with someone better able to capture it
– ENHANCE — increase the probability or the impact
– ACCEPT — take it if it arrives, but do nothing to cause it
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
223

## Slide 224
THE FOUR THINGS PEOPLE FORGET
After the Response — What's Left
1
Trigger condition
The observable signal that the risk is developing. A response with no trigger is never implemented in time.
2
Secondary risk
A NEW risk created directly by your response. Transferring risk to a vendor creates vendor dependency risk.
3
Residual risk
What REMAINS after the response is implemented. It must be accepted knowingly.
4
Fallback plan
What you do if the primary response fails. Funded by the contingency reserve.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
224

## Slide 225
TOPIC 03 · ACTIVITY 21
Plan Risk Responses with GenAI
ACTIVITY 21
A risk register with no responses is a list of things you will be surprised by. You will plan a response for every priority risk and check for the second-order effects that responses create.
You'll produce
A response plan for every priority risk, with owners, triggers and fallback plans.
Tools: GenAI tool · your risk register from Activities 18-19
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
225

## Slide 226
TOPIC 03 · ACTIVITY 21
Plan Risk Responses with GenAI
ACTIVITY 21
PROMPT GenAI WITH
For each priority risk [paste], recommend one primary response strategy from avoid, transfer, mitigate, accept, escalate, exploit, share or enhance. Give the action, owner, trigger, fallback and response cost.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
226

## Slide 227
ACTIVITY 21 · CHECK YOUR WORK
Plan Risk Responses with GenAI
✅ Check your work
Every priority risk has a correctly-named strategy, an owner, an observable trigger, an identified secondary and residual risk, and your top three have fallback plans.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
227

## Slide 228
PROCUREMENT
Plan Procurement and Manage Contracts
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
228

## Slide 229
BUYING FROM OUTSIDE
Planning the Procurement Strategy
1
Any external resource
Procurement covers vendors, consultants, contractors and equipment.
2
Agreement vs contract
You can have an agreement without a contract — but never a contract without an agreement.
3
Claims
Arise when buyer and seller cannot agree that a change occurred.
4
ADR
If a claim is unresolved, Alternative Dispute Resolution is used — as defined in the contract.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
229

## Slide 230
CHOOSING THE RIGHT DOCUMENT
Bid Documents
1
RFI — Request for Information
When you need more information about what sellers can provide.
2
RFP — Request for Proposal
When the solution is not obvious and you need sellers to propose one.
3
RFQ — Request for Quote
When you know exactly what you want and need a price.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
230

## Slide 231
THE MOST IMPORTANT PROCUREMENT DECISION
Contract Types — Who Carries the Risk
Contract type
Variants
Who carries cost-overrun risk / when to use
Fixed Price
Firm Fixed Price; FP + Incentive Fee; FP with Economic Adjustment
SELLER carries it. Use when scope is straightforward and requirements are well defined
Cost Reimbursable
Cost plus Fixed Fee; plus Incentive Fee; plus Award Fee
BUYER carries it. Use to incentivise the seller, or when work is expected to change
Time and Materials
Hybrid of both
Shared. Use when a precise statement of work is unavailable, or for staff augmentation
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
231

## Slide 232
WHAT MUST BE IN IT
Components of a Contract
1
Description of work — deliverables and scope
2
Delivery date and schedule information
3
Responsibilities of both parties
4
Price and payment terms
5
Provisions for termination
6
Guarantees and warranties
7
Intellectual property
8
Security, confidentiality and data privacy
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
232

## Slide 233
WHEN THINGS GO WRONG
Managing Contract Disputes
1
Warranty
A promise, explicit or implied, that goods or services meet a predetermined standard.
2
Waiver
One party agrees to forfeit a claim without the other becoming liable.
3
Breach of contract
Failure to meet some or all obligations — may result in damages or litigation.
4
Cease and desist
A letter instructing a party to stop allegedly illegal activity.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
233

## Slide 234
TOPIC 03 · ACTIVITY 22
Plan Procurement and Manage Contracts with GenAI
ACTIVITY 22
Procurement transfers risk — but only if you choose the right contract type. You will use GenAI to draft procurement documents and to reason about where risk actually sits in each contract type.
You'll produce
A procurement strategy with a justified contract type and a drafted RFP outline.
Tools: GenAI tool · Claude
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
234

## Slide 235
TOPIC 03 · ACTIVITY 22
Plan Procurement and Manage Contracts with GenAI
ACTIVITY 22
PROMPT GenAI WITH
Compare Firm Fixed Price, Cost Plus Fixed Fee and Time and Materials for this procurement. State who carries cost-overrun risk, when each contract fits, and recommend one option using the supplied evaluation criteria.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
235

## Slide 236
ACTIVITY 22 · CHECK YOUR WORK
Plan Procurement and Manage Contracts with GenAI
✅ Check your work
You have the right bid document type, a contract type justified by who should carry scope risk, and a component checklist including IP, data privacy and dispute resolution.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
236

## Slide 237
MONITOR & CONTROL
Monitor Work, Control Change and Measure Performance
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
237

## Slide 238
WHAT YOU DO CONTINUOUSLY
Monitoring and Controlling Project Work
1
Evaluate project progress against the baseline
2
Manage issues and impediments
3
Manage changes through integrated change control
4
Support project team performance
5
Implement ongoing improvements
6
Monitor the external business environment
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
238

## Slide 239
WHY BASELINES MOVE
Causes of Project Change
1
Inaccurate initial estimates
2
New or changed regulations
3
Missed requirements
4
Specification changes
5
Changes to the business case
6
External market or technology shifts
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
239

## Slide 240
FOUR TYPES — ONLY ONE CHANGES A BASELINE
Types of Change Request
1
Corrective action
Realigns the performance of project work with the project management plan.
2
Preventive action
Ensures FUTURE performance aligns with the plan.
3
Defect repair
Modifies a non-conformance within the project.
4
Change
Modifies a project baseline — this is the one that needs formal approval.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
240

## Slide 241
CONTROLLING CHANGE
Integrated Change Control
1
Raise the change request
▶
2
Analyse impacts on scope, schedule, cost, quality and risk
▶
3
Record it in the Change Log
▶
4
Change Control Board approves, defers or rejects
▶
5
Communicate the outcome and update baselines
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
241

## Slide 242
SIX WAYS TO REPORT
Reporting on Performance
1
Milestone schedule
High-level visualisation of progress against planned dates.
2
Quality reports
Charts and reports based on quality metrics.
3
Earned value reports
Graphs and values based on the EVM equations.
4
Variance analysis
Comparing actual against expected results.
5
Work performance reports
The formal status representation.
6
Dashboards
Visual progress summaries representing a larger data set.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
242

## Slide 243
EARNED VALUE
Measure Performance Objectively
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
243

## Slide 244
EVERYTHING ELSE IS DERIVED FROM THESE
The Three Base Values
1
PV — Planned Value
The authorised budget assigned to the work SCHEDULED to be done by now.
2
EV — Earned Value
The budget for the work ACTUALLY COMPLETED, in budget terms.
3
AC — Actual Cost
The cost actually INCURRED for the work performed.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
244

## Slide 245
ARE YOU OVER OR BEHIND?
Variance Analysis
Cost
Schedule
• Cost Variance
– CV = EV – AC
– POSITIVE is good — under budget
– NEGATIVE is bad — over budget
– Measured in dollars
• Schedule Variance
– SV = EV – PV
– POSITIVE is good — ahead of schedule
– NEGATIVE is bad — behind schedule
– Measured in dollars, not days
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
245

## Slide 246
RATIOS TELL YOU THE RATE
Performance Indices
Cost
Schedule
• Cost Performance Index
– CPI = EV ÷ AC
– Greater than 1 is good
– Less than 1 means you are over budget
– CPI of 0.84 means you get 84 cents of value per dollar spent
• Schedule Performance Index
– SPI = EV ÷ PV
– Greater than 1 is good
– Less than 1 means you are behind schedule
– SPI of 0.80 means you are progressing at 80% of the planned rate
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
246

## Slide 247
WHERE WILL WE END UP?
Forecasting
1
BAC — Budget At Completion
The total approved budget for the project.
2
EAC — Estimate At Completion
What the project will now cost in total. EAC = BAC ÷ CPI.
3
ETC — Estimate To Complete
What remains to be spent. ETC = EAC – AC.
4
VAC — Variance At Completion
How far off budget you will finish. VAC = BAC – EAC.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
247

## Slide 248
TOPIC 03 · ACTIVITY 23
Earned Value Analysis with GenAI
ACTIVITY 23
Earned value is the one technique that tells you objectively whether you are ahead or behind, over or under. You will compute it by hand first, then test whether GenAI gets it right.
You'll produce
A complete earned value analysis with variances, indices and a forecast.
Tools: GenAI tool · calculator
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
248

## Slide 249
TOPIC 03 · ACTIVITY 23
Earned Value Analysis with GenAI
ACTIVITY 23
PROMPT GenAI WITH
Using the supplied baseline, completion and actual-cost data, calculate PV, EV, AC, CV, SV, CPI, SPI, EAC and ETC. Show the formula and substitution for every result, then interpret the project status.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
249

## Slide 250
ACTIVITY 23 · CHECK YOUR WORK
Earned Value Analysis with GenAI
✅ Check your work
You can compute PV, EV, AC, CV, SV, CPI, SPI and EAC unaided for a fresh scenario, and you found at least one error in the AI's version.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
250

## Slide 251
CONTROL QUALITY
Control Quality and Close the Project
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
251

## Slide 252
MAKING SURE IT IS RIGHT
Quality Control
1
Assess approaches
Evaluate the quality of project approaches and activities.
2
Inspect and test
Evaluate deliverable quality through inspection and testing.
3
Review and audit
Evaluate project activities and processes through reviews and audits.
4
Detect and prevent
Focus on detecting AND preventing errors and defects.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
252

## Slide 253
FIVE STEPS, IN ORDER
The Control Quality Process
1
Use CHECK SHEETS to collect the data
▶
2
Plot the data on a HISTOGRAM
▶
3
Find the vital few with a PARETO CHART
▶
4
Find the root cause with CAUSE-AND-EFFECT analysis
▶
5
Understand correlation with SCATTER analysis
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
253

## Slide 254
IS THE PROCESS IN CONTROL?
Control Charts
1
What it shows
The predictability, behaviour and stability of a process over time.
2
Best for
Repetitive processes with predictable results.
3
Control limits
Come from the PROCESS — what it actually does.
4
Specification limits
Come from the CUSTOMER — what they require. A process can be in control and still fail spec.
5
The rule of seven
Seven consecutive points on one side of the mean, or seven rising or falling, indicates a trend.
6
Correlation chart
Shows the relationship between two variables — a process element against a quality defect.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
254

## Slide 255
TOPIC 03 · ACTIVITY 24
Control Quality with GenAI — Check Sheets and Control Charts
ACTIVITY 24
Quality control is about detecting problems from data rather than opinion. You will collect data on a check sheet and plot a control chart, applying the rule of seven.
You'll produce
A check sheet of collected data and a control chart with limits and a trend assessment.
Tools: GenAI tool · Check Sheets.xlsx · Control Chart.xlsx
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
255

## Slide 256
TOPIC 03 · ACTIVITY 24
Control Quality with GenAI — Check Sheets and Control Charts
ACTIVITY 24
PROMPT GenAI WITH
Use the supplied defect log to produce a check-sheet summary and control-chart data. Calculate the centre line and control limits, identify any special-cause signal and explain what additional evidence is needed.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
256

## Slide 257
ACTIVITY 24 · CHECK YOUR WORK
Control Quality with GenAI — Check Sheets and Control Charts
✅ Check your work
Your control chart has a mean and both control limits, you have checked for runs of seven, and you can distinguish control limits from specification limits.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
257

## Slide 258
RISK IS NOT A ONE-OFF EXERCISE
Monitoring Risk Through Execution
1
Continuously monitor
Status, probability and impact of every open risk.
2
Identify new risks
New risks emerge as the project and its environment change.
3
Reassess and close
Reassess current risks; close risks that are now outdated.
4
Update the reserve
Track how much contingency remains against how much risk remains.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
258

## Slide 259
NOT EVERY CLOSURE IS A SUCCESS
Why Projects or Phases Close
1
Successful completion
Stakeholders accept the deliverables against the acceptance criteria.
2
Requirements change
The need the project answered no longer exists.
3
No longer feasible
The deliverable cannot be produced as envisaged.
4
Business case changes
An internal decision removes the justification.
5
Legal or regulatory change
An external change prohibits progress.
6
Funding or risk
Financial support ends, or risks make completion impossible.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
259

## Slide 260
THE CLOSURE CHECKLIST
Close Project or Phase — Activities
1
Customer acceptance of the deliverables
2
Transition of the product to the customer
3
Notify enterprise functions; update organisational process assets
4
Prepare the final report
5
Conclude external obligations — legal, regulatory, contractual
6
Close all accounts in the financial system
7
Archive all project information
8
Release resources — people, financial and physical
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
260

## Slide 261
MAKING ADOPTION STICK
Transition and Handover
1
Training
End users need training on the new product or service.
2
Documentation
The product and deliverable documentation must be handed over.
3
Communication
Effective communication between the project team and the organisation.
4
Hypercare
Post-implementation support during the period immediately after go-live.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
261

## Slide 262
WHAT GOES IN THE FINAL REPORT
Finalise Lessons Learned
1
Scope changes and why they happened
2
Schedule impacts and their causes
3
Risks and issues that materialised
4
Stakeholder relationships
5
Vendor relationships and performance
6
Artifacts worth reusing and recommendations
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
262

## Slide 263
TOPIC 03 · ACTIVITY 25
Monitor, Control Change and Close the Project with GenAI
ACTIVITY 25
The final activity runs the end of the project lifecycle: processing a change request through integrated change control, then closing the project and capturing lessons learned with GenAI's help.
You'll produce
A processed change request with impact analysis, and a project closure report.
Tools: GenAI tool · Digital AI Transformation Roadmap Studio (alfredang.github.io/digitaltransformation) · Change Request template
Step-by-step instructions: see your Learner Guide
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
263

## Slide 264
TOPIC 03 · ACTIVITY 25
Monitor, Control Change and Close the Project with GenAI
ACTIVITY 25
PROMPT GenAI WITH
Analyse each change request for its effect on scope, schedule, cost, quality, resources and risk. State confidence in each estimate, recommend an approve, reject or defer decision, and draft the closure actions for approved changes.
⚠ THEN CHECK IT
GenAI gives you a fast first draft. Check every figure, source and assumption before you use it.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
264

## Slide 265
ACTIVITY 25 · CHECK YOUR WORK
Monitor, Control Change and Close the Project with GenAI
✅ Check your work
Your change request is correctly classified with impacts on all five dimensions, it has been through the CCB path, and your closure report covers acceptance, transition, contracts, archiving and resource release.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
265

## Slide 266
TOPIC RECAP
Recap — Managing Project Risks with GenAI
• Anticipate potential risks to project delivery (A3).
• Prioritise risks by probability and impact for further action.
• Quantify risk exposure to support a financial decision.
• Devise risk mitigation measures to ensure project success (A4).
• Select the right contract type and manage procurement risk.
• Measure project performance objectively and forecast the outcome.
• Detect whether a process is stable and in control.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
266

## Slide 267
WRAP-UP
Course Summary & Next Steps
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
267

## Slide 268
LEARNING OUTCOMES
What You Achieved
1
LO1 · Initiation & Planning
Charters, business cases, stakeholder maps, RACI, requirements, WBS, schedules and budgets — all built with GenAI.
2
LO2 · Execution & Delivery
Performance reporting, knowledge capture, root cause analysis, resource and budget optimisation, team and communications.
3
LO3 · Risk & Closure
Risk identification and analysis, response planning, procurement, change control, earned value and project closure.
4
The habit that matters
You prompt for a first draft, then verify every figure, source and assumption before it leaves your hands.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
268

## Slide 269
NEXT STEPS
Applying This at Work Next Week
1
Start small
Pick one artifact — a status report or a risk register — and draft it with GenAI.
2
Reuse your prompt library
The prompts you built in Activity 1 work on your real projects.
3
Check your policy
Confirm what your organisation allows you to put into a GenAI tool.
4
Keep the ed-tools
RACI, BMC, Design Thinking, Scrum and the Roadmap Studio are free and need no install.
5
Verify everything
Especially arithmetic, sources and anything about a named person.
6
Share the practice
Show one colleague the prompting pattern that helped you most.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
269

## Slide 270
BEFORE YOU GO
Course Feedback
1
Why it matters
Your feedback tells us what worked and what to improve for the next run.
2
Where
Complete the feedback form on the LMS at lms-tms.tertiaryinfotech.com
3
Your certificate
Your certificate is issued through the same portal.
4
When
Please complete it before you leave the classroom.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
270

## Slide 271
CONTINUE YOUR LEARNING
Recommended Next Courses
1
Agile Project Management for Business
2
Mastering Agile Project Management for IT Projects
3
Business Analysis with Generative AI
4
Data Analytics with Generative AI
5
Generative AI for Productivity
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
271

## Slide 272
WE'RE HERE TO HELP
Support
1
Email
enquiry@tertiaryinfotech.com
2
Telephone
+65 6100 0613
3
Website
www.tertiarycourses.com.sg
4
LMS / TMS
https://lms-tms.tertiaryinfotech.com
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
272

## Slide 273
SEE YOU AT THE NEXT COURSE
Thank You!
You can now plan, execute and control a project with GenAI as your co-pilot — and you know exactly where its judgement ends and yours begins.
Generative AI for Project Management · C013
© 2026 Tertiary Infotech Academy Pte Ltd
273